Invitation For Bids

----------------------------------------------------------------------------------------------------------------

The Kenya Electricity Transmission Company Limited has applied for funds from the Agence Française de Développement (the French Development Agency) towards the cost of the 400/132kV Makindu Substation.  It is intended that part of the proceeds of this loan will be applied to eligible payments under the contract for Design, Manufacture, Supply, Installation, & Commissioning of the 400/132kV Makindu Substation.

The Kenya Electricity Transmission Company Limited now invites sealed bids from pre-qualified eligible bidders for the design, supply and installation of the 400/132kV Makindu Substation (“the Facilities”).

Pre-qualified eligible bidders may obtain further information from and inspect the bidding documents at the office of

Attention: Senior Manager Supply Chain

Kenya Electricity Transmission Company Limited

Second Floor, Kawi Complex, Block B

Off Popo Road, Off Red Cross Road, South C

A complete set of bidding documents may be obtained from KETRACO website (https://ketraco.co.ke/procurement/tenders/open-tenders) free of charge by interested pre-qualified bidders.

Bids must be delivered to the above office on or before 10.00 am on 25th October 2024 and must be accompanied by a bid security of Euros 700,000.

Bids will be opened in the presence of bidders’ representatives who choose to attend at 10.00 am on 25th October 2024 at the office indicated above.

# PROCUREMENT DOCUMENTS

Bidding Document for
Procurement of Plant Design, Supply, and Installation

Procurement of:

400/132 kV Makindu Substation

ICB No: KETRACO/ST/007/2024

Project: 400/132kV Makindu Substation

Employer: Kenya Electricity Transmission Company Limited

Country: Kenya

Issued on: 26th August 2024

# Standard Bidding Document

Table of Contents

PART 1 – Bidding Procedures	3

OPTION A:  Single Stage Bidding	4

Section I.  Instructions to Bidders	5

Section II.  Bid Data Sheet	31

Section III.  Evaluation and Qualification Criteria (Following Prequalification)	36

Section IV.  Bidding Forms	53

Section V.  Eligibility criteria and social and environmental responsibility	102

Section VI. Agency Policy - Corrupt and Fraudulent Practices – Social and Environmental Responsibility	104

##### PART 1 – Bidding Procedures

##### OPTION A:  Single Stage Bidding

###### Section I. Instructions to Bidders

Table of Clauses

A.	General	7

1.	Scope of Bid	7

2.	Source of Funds	7

3.	Corrupt and Fraudulent Practices	7

4.	Eligible Bidders	7

5.	Eligible Plant and Installation Services	9

B.	Contents of Bidding Document	9

6.	Sections of  Bidding Document	9

7.	Clarification of Bidding Document, Site Visit, Pre-Bid Meeting	10

8.	Amendment of Bidding Document	11

C.	Preparation of Bids	12

9.	Cost of Bidding	12

10.	Language of Bid	12

11.	Documents Comprising the Bid	12

12.	Letter of Bid, Statement of Integrity and Schedules	13

13.	Alternative Bids	13

14.	Documents Establishing the Eligibility of the  Plant and Installation Services	14

15.	Documents Establishing the Eligibility and Qualifications of the Bidder	14

16.	Documents establishing conformity of the Plant and Installation Services	14

17.	Bid Prices and Discounts	14

18.	Currencies of Bid and Payment	17

19.	Period of Validity of Bids	17

20.	Bid Security	18

21.	Format and Signing of Bid	19

D.	Submission and Opening of Bids	20

22.	Submission, Sealing and Marking of Bids	20

23.	Deadline for Submission of Bids	21

24.	Late Bids	21

25.	Withdrawal, Substitution, and Modification of Bids	21

26.	Bid Opening	21

E.	Evaluation and Comparison of Bids	23

27.	Confidentiality	23

28.	Clarification of Bids	23

29.	Deviations, Reservations, and Omissions	23

30.	Determination of  Responsiveness	24

31.	Nonmaterial Nonconformities	24

32.	Correction of Arithmetical Errors	25

33.	Conversion to Single Currency	25

34.	Margin of Preference	25

35.	Evaluation of Bids	25

36.	Comparison of Bids	27

37.	Eligibility and Qualification of the Bidder	27

38.	Employer’s Right to Accept Any Bid, and to Reject Any or All Bids	28

F.	Award of Contract	28

39.	Award Criteria	28

40.	Notification of Award	28

41.	Signing of Contract	29

42.	Performance Security	29

| Section I. Instructions to Bidders |  |
| --- | --- |
|  | General |
| Scope of Bid | - In connection with the Invitation for Bids indicated in the Bid Data Sheet (BDS), the Employer, as indicated in the BDS, issues this Bidding Document for the procurement of Plant and Installation Services as specified in Section VII, Employer’s Requirements. The name, identification, and number of lots (contracts) of the International Competitive Bidding (ICB) are provided in the BDS. - Throughout these Bidding Documents: - the term “in writing” means communicated in written form and delivered against receipt; - except where the context requires otherwise, words indicating the singular also include the plural and words indicating the plural also include the singular; and - “day” means calendar day. |
| Source of Funds | The Employer has received or has applied for financing (hereinafter called “funds”) from the Agence Française de Développement (hereinafter called “the Agency”) toward the project named in the BDS. The Employer intends to apply a portion of the funds to eligible payments under the contract(s) for which these Bidding Documents are issued. |
| Corrupt and Fraudulent Practices | The Agency requires compliance with its policy in regard to corrupt and fraudulent practices as set forth in Section VI. In further pursuance of this policy, Bidders shall permit and shall cause its agents (whether declared or not), sub-contractors, sub-consultants, service providers, or suppliers and any personnel thereof, to permit the Agency to inspect all accounts, records and other documents relating to any prequalification process, bid submission, and contract performance (in the case of award), and to have them audited by auditors appointed by the Agency. |
| Eligible Bidders | A Bidder may be a private entity or a government-owned entity—subject to ITB 4.3-or any combination of such entities in the form of a joint venture(JV) under an existing agreement or with the intent to enter into such an agreement supported by a letter of intent. In the case of a joint venture: (a) unless otherwise specified in the BDS, all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms, and (b) the JV shall nominate a Representative who shall have the authority to conduct all business for and on behalf of any and all the partners of the JVA during the bidding process and, in the event the JV is awarded the Contract, during contract execution. Unless specified in the BDS, there is no limit on the number of members in a JV. |
|  | A Bidder shall not have a conflict of interest. All Bidders found to have a conflict of interest shall be disqualified. A Bidder may be considered to have a conflict of interest for the purpose of this bidding process, if the Bidder: - directly or indirectly controls, is controlled by or is under common control with another Bidder; or - receives or has received any direct or indirect subsidy from another Bidder; or - has the same legal representative as another Bidder; or - has a relationship with another Bidder, directly or through common third parties, that puts it in a position to influence the bid of another Bidder, or influence the decisions of the Employer regarding this bidding process; or - participates in more than one bid in this bidding process. Participation by a Bidder in more than one Bid will result in the disqualification of all Bids in which such Bidder is involved. However, this does not limit the inclusion of the same subcontractor in more than one bid; or - any of its affiliates participated as a consultant in the preparation of the design or technical specifications of the Plant and Installation Services that are the subject of the present bid; or - any of its affiliates has been hired (or is proposed to be hired) by the Employer as Project Manager for the Contract implementation; or - has a close business or family relationship with a professional staff of the Employer (or of the project implementing agency, or of a recipient of a part of the loan) who: (i) are directly or indirectly involved in the preparation of the bidding documents or specifications of the contract, and/or the bid evaluation process of such contract; or (ii) would be involved in the implementation or supervision of such contract unless the conflict stemming from such relationship has been resolved in a manner acceptable to the Agency throughout the procurement process and execution of the contract. |
|  | The Agency’s eligibility criteria to bid are described in Section V – Eligibility criteria and social and environmental responsibility. |
|  | A Bidder shall not be under suspension from bidding by the Employer as the result of the operation of a Bid–Securing Declaration. |
|  | Bidders shall provide such evidence of their continued eligibility satisfactory to the Employer, as the Employer shall reasonably request. In case a prequalification process has been conducted prior to the bidding process, this bidding is open only to prequalified Bidders. |
| Eligible Plant and Installation Services | The Plant and Installation Services to be supplied under the Contract and financed by the Agency may have their origin in any country, subject to the restrictions specified in Section V, Eligibility criteria and social and environmental responsibility, and all expenditures under the Contract will not contravene such restrictions. At the Employer’s request, Bidders may be required to provide evidence of the origin of Plant and Installation Services. |
|  | Contents of Bidding Document |
| Sections of Bidding Document | The Bidding Document consists of Parts 1, 2, and 3, which include all the Sections indicated below, and should be read in conjunction with any Addenda issued in accordance with ITB 8. PART 1 Bidding Procedures - Section I. Instructions to Bidders (ITB) - Section II. Bid Data Sheet (BDS) - Section III. Evaluation and Qualification Criteria - Section IV. Bidding Forms - Section V. Eligibility criteria and social and environmental responsibility - Section VI. Agency Policy-Corrupt and Fraudulent Practices PART 2 Employer’s Requirements - Section VII. Employer’s Requirements PART 3 Conditions of Contract and Contract Forms - Section VIII. General Conditions (GC) - Section IX. Particular Conditions (PC) - Section X. Contract Forms |
|  | The Invitation for Bids issued by the Employer is not part of the Bidding Document. |
|  | Unless obtained directly from the Employer, the Employer is not responsible for the completeness of the Bidding Document, responses to requests for clarification, the minutes of the pre-Bid meeting (if any), or Addenda to the Bidding Documents in accordance with ITB 8. In case of any contradiction, documents obtained directly from the Employer shall prevail. |
|  | The Bidder is expected to examine all instructions, forms, terms, and specifications in the Bidding Document and to furnish with its bid all information and documentation as is required by the Bidding Documents. |
| Clarification of Bidding Document, Site Visit, Pre-Bid Meeting | Any prospective Bidder requiring clarifications of the Bidding Documents shall contact the Employer in writing at the Employer’s address indicated in the BDS or raise his enquiries during the pre-bid meeting if provided for in accordance with ITB 7.4. The Employer will respond to any request for clarification, provided that such request is received no later than fourteen (14) days prior to the deadline for submission of bids. The Employer shall forward copies of its response to all Bidders who have acquired the Bidding Documents in accordance with ITB 6.3, including a description of the inquiry but without identifying its source. If so specified in the BDS, the Employer shall also promptly publish its response at the web page identified in the BDS. Should the clarification result in changes to the essential elements of the Bidding Documents, the Employer shall amend the Bidding Documents following the procedure under ITB 8 and ITB 23.2. |
|  | The Bidder is advised to visit and examine the site where the plant is to be installed and its surroundings and obtain for itself on its own responsibility all information that may be necessary for preparing the bid and entering into a contract for the provision of Plant and Installation Services. The costs of visiting the site shall be at the Bidder’s own expense. |
|  | The Bidder and any of its personnel or agents will be granted permission by the Employer to enter upon its premises and lands for the purpose of such visit, but only upon the express condition that the Bidder, its personnel, and agents will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. |
|  | The Bidder’s designated representative is invited to attend a pre-bid meeting, if provided for in the BDS. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. |
|  | The Bidder is requested, as far as possible, to submit any questions in writing, to reach the Employer not later than one week before the meeting. |
|  | Minutes of the pre-bid meeting, including the text of the questions raised without identifying the source, and the responses given, together with any responses prepared after the meeting, will be transmitted promptly to all Bidders who have acquired the Bidding Document in accordance with ITB 6.3. Any modification to the Bidding Document that may become necessary as a result of the pre-bid meeting shall be made by the Employer exclusively through the issue of an Addendum pursuant to ITB 8 and not through the minutes of the pre-bid meeting. Nonattendance at the pre-bid meeting will not be a cause for disqualification of a Bidder. |
| Amendment of Bidding Document | At any time prior to the deadline for submission of bids, the Employer may amend the Bidding Document by issuing addenda. |
|  | Any addendum issued shall be part of the Bidding Document and shall be communicated in writing to all who have obtained the Bidding Document from the Employer in accordance with ITB 6.3. Employer shall also promptly publish the addendum at the web page in accordance with ITB 7.1. |
|  | To give prospective Bidders reasonable time in which to take an addendum into account in preparing their bids, the Employer may, at its discretion, extend the deadline for the submission of bids, pursuant to ITB 23.2. |
|  | Preparation of Bids |
| Cost of Bidding | The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Employer shall not be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. |
| Language of Bid | The Bid, as well as all correspondence and documents relating to the bid exchanged by the Bidder and the Employer, shall be written in the language specified in the BDS. Supporting documents and printed literature that are part of the Bid may be in another language provided they are accompanied by an accurate translation of the relevant passages in the language specified in the BDS, in which case, for purposes of interpretation of the Bid, such translation shall govern. |
| Documents Comprising the Bid | The Bid submitted by the Bidder shall comprise the following: (a) Letter of Bid, in accordance with ITB 12; (b) Completed schedules as required, including Price Schedules, in accordance with ITB 12 and 17; (c) Statement of Integrity, Eligibility and Social and Environmental Responsibility duly signed; (d) Bid Security or Bid Securing Declaration, in accordance with ITB 20; (e) alternative bids, if permissible, in accordance with ITB 13; (f) written confirmation authorizing the signatory of the Bid to commit the Bidder, in accordance with ITB 21.2; (g) documentary evidence established in accordance with ITB 14.1 that the Plant and Installation Services offered by the Bidder in its bid or in any alternative bid, if permitted, are eligible; (h) documentary evidence in accordance with ITB 15 establishing the Bidder’s eligibility and qualifications to perform the contract if its Bid is accepted; (i) documentary evidence established in accordance with ITB 16 that the Plant and Installation Services offered by the Bidder conform to the Bidding Document; (j) in the case of a bid submitted by a JV, JV agreement, or letter of intent to enter into a JV including a draft agreement, indicating at least the parts of the Plant to be executed by the respective partners; (k) List of subcontractors, in accordance with ITB 16.2; and (l) any other document required in the BDS. The Bidder shall furnish in the Letter of Bid information on commissions and gratuities, if any, paid or to be paid to agents or any other party relating to this Bid. |
| Letter of Bid, Statement of Integrity and Schedules | The Letter of Bid, the Statement of Integrity and the Schedules, including the appropriate Price Schedules, shall be prepared using the relevant forms furnished in Section IV, Bidding Forms. The Letter of Bid and Statement of Integrity must be completed without any alteration to the text, and no substitute shall be accepted except as provided under ITB 21.2. All blank spaces shall be filled in with the information requested. |
| Alternative Bids | The BDS indicates whether alternative bids are allowed. If they are allowed, the BDS will also indicate whether they are permitted in accordance with ITB 13.3, or invited in accordance with ITB13.2 and/or ITB 13.4. |
|  | When alternatives to the Time Schedule are explicitly invited, a statement to that effect will be included in the BDS, and the method of evaluating different time schedules will be described in Section III, Evaluation and Qualification Criteria. |
|  | Except as provided under ITB 13.4 below, Bidders wishing to offer technical alternatives to the Employer’s requirements as described in the bidding document must also provide: (i) a price at which they are prepared to offer a plant meeting the Employer’s requirements; and (ii) all information necessary for a complete evaluation of the alternatives by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, and proposed installation methodology and other relevant details. Only the technical alternatives, if any, of the lowest evaluated Bidder conforming to the basic technical requirements shall be considered by the Employer. |
|  | When bidders are invited in the BDS to submit alternative technical solutions for specified parts of the facilities, such parts shall be described in Section VII, Employer’s Requirements. Technical alternatives that comply with the performance and technical criteria specified for the Plant and Installation Services shall be considered by the Employer on their own merits, pursuant to ITB 35. |
| Documents Establishing the Eligibility of the Plant and Installation Services | To establish the eligibility of the Plant and Installation Services in accordance with ITB Clause 5, Bidders shall complete the country of origin declarations in the Price Schedule Forms, included in Section IV, Bidding Forms. |
| Documents Establishing the Eligibility and Qualifications of the Bidder | To establish its eligibility and qualifications to perform the Contract in accordance with Section III, Evaluation and Qualification Criteria, the Bidder shall provide the information requested in the corresponding information sheets included in Section IV, Bidding Forms. |
| Documents establishing conformity of the Plant and Installation Services | The Bidder shall furnish the information stipulated in Section IV, in sufficient detail to demonstrate substantial responsiveness of the Bidders’ proposal to the Employer’s requirements and the completion time. For major items of Plant and Installation Services as listed by the Employer in Section III, Evaluation and Qualification Criteria, which the Bidder intends to purchase or subcontract, the Bidder shall give details of the name and nationality of the proposed Subcontractors, including manufacturers, for each of those items. In addition, the Bidder shall include in its bid information establishing compliance with the requirements specified by the Employer for these items. Quoted rates and prices will be deemed to apply to whichever Subcontractor is appointed, and no adjustment of the rates and prices will be permitted. The Bidder shall be responsible for ensuring that any Subcontractor proposed complies with the requirements of ITB 4, and that any plant, or services to be provided by the Subcontractor comply with the requirements of ITB 5 and ITB 15.1 |
| Bid Prices and Discounts | Unless otherwise specified in the BDS, bidders shall quote for the entire Plant and Installation Services on a “single responsibility” basis such that the total bid price covers all the Contractor’s obligations mentioned in or to be reasonably inferred from the bidding document in respect of the design, manufacture, including procurement and subcontracting (if any), delivery, construction, installation and completion of the plant. This includes all requirements under the Contractor’s responsibilities for testing, pre-commissioning and commissioning of the plant and, where so required by the bidding document, the acquisition of all permits, approvals and licenses, etc.; the operation, maintenance and training services and such other items and services as may be specified in the Bidding Document, all in accordance with the requirements of the General Conditions. Items against which no price is entered by the Bidder will not be paid for by the Employer when executed and shall be deemed to be covered by the prices for other items. Bidders are required to quote the price for the commercial, contractual and technical obligations outlined in the bidding document. Bidders shall give a breakdown of the prices in the manner and detail called for in the Price Schedules included in Section IV, Bidding Forms. Depending on the scope of the Contract, the Price Schedules may comprise up to the six (6) schedules listed below. Separate numbered Schedules included in Section IV, Bidding Forms, from those numbered 1-4 below, shall be used for each of the elements of the Plant and Installation Services. The total amount from each Schedule corresponding to an element of the Plant and Installation Services shall be summarized in the schedule titled Grand Summary, (Schedule 5), giving the total bid price(s) to be entered in the Letter of Bid. Schedule No. 1 Plant (including Mandatory Spare Parts) Supplied from Abroad Schedule No. 2 Plant (including Mandatory Spare Parts) Supplied from within the Employer’s Country Schedule No. 3 Design Services Schedule No. 4 Installation Services Schedule No. 5 Grand Summary (Schedule Nos. 1 to 4) Schedule No. 6 Recommended Spare Parts Bidders shall note that the plant and equipment included in Schedule Nos. 1 and 2 above exclude materials used for civil, building and other construction works. All such materials shall be included and priced under Schedule No. 4, Installation Services. In the Schedules, bidders shall give the required details and a breakdown of their prices as follows: (a) Plant to be supplied from abroad (Schedule No. 1): The price of the plant shall be quoted on CIP-named place of destination basis as specified in the BDS (b) Plant manufactured within the Employer’s country (Schedule No. 2): (i) The price of the plant shall be quoted on an EXW Incoterm basis (such as “ex-works,” “ex-factory,” “ex-warehouse” or “off-the-shelf,” as applicable), (ii) Sales tax and all other taxes payable in the Employer’s country on the plant if the contract is awarded to the Bidder, and (iii) The total price for the item. (c) Design Services (Schedule No. 3). (d) Installation Services shall be quoted separately (Schedule No. 4) and shall include rates or prices for local transportation to named place of final destination as specified in the BDS, insurance and other services incidental to delivery of the plant, all labor, contractor’s equipment, temporary works, materials, consumables and all matters and things of whatsoever nature, including operations and maintenance services, the provision of operations and maintenance manuals, training, etc., where identified in the Bidding Document, as necessary for the proper execution of the installation and other services, including all taxes, duties, levies and charges payable in the Employer’s country as of twenty-eight (28) days prior to the deadline for submission of bids unless otherwise specified in the BDS. (e) Recommended spare parts shall be quoted separately (Schedule 6) as specified in either subparagraph (a) or (b) above in accordance with the origin of the spare parts. The current edition of Incoterms, published by the International Chamber of Commerce shall govern. The prices shall be either fixed or adjustable as specified in the BDS. In the case of Fixed Price, prices quoted by the Bidder shall be fixed during the Bidder’s performance of the contract and not subject to variation on any account. A bid submitted with an adjustable price quotation will be treated as non-responsive and rejected. In the case of Adjustable Price, prices quoted by the Bidder shall be subject to adjustment during performance of the contract to reflect changes in the cost elements such as labor, material, transport and contractor’s equipment in accordance with the procedures specified in the corresponding Appendix to the Contract Agreement. A bid submitted with a fixed price quotation will not be rejected, but the price adjustment will be treated as zero. Bidders are required to indicate the source of labor and material indices in the corresponding Form in Section IV, Bidding Forms, and to furnish the indices and weightings for the price adjustment formulae. The Employer may require the Bidder to justify its proposed indices and weightings. |
|  | If so indicated in ITB 1.1, bids are being invited for individual lots (contracts) or for any combination of lots (packages). Bidders wishing to offer any price reduction (discount) for the award of more than one Contract shall specify in their Letter of Bid the price reductions applicable to each package, or alternatively, to individual Contracts within the package, and the manner in which the price reductions will apply. |
|  | Bidders wishing to offer any unconditional discount shall specify in their Letter of Bid the offered discounts and the manner in which price discounts will apply. |
| Currencies of Bid and Payment | The currency(ies) of the bid shall be, as specified in the BDS. Bidders may be required by the Employer to justify, to the Employer’s satisfaction, their local and foreign currency requirements. |
| Period of Validity of Bids | Bids shall remain valid for the period specified in the BDS after the bid submission deadline date prescribed by the Employer. A bid valid for a shorter period shall be rejected by the Employer as non-responsive. |
|  | In exceptional circumstances, prior to the expiration of the bid validity period, the Employer may request Bidders to extend the period of validity of their bids. The request and the responses shall be made in writing. If a bid security is requested in accordance with ITB 20, the Bidder granting the request shall also extend the bid security for twenty-eight (28) days beyond the deadline of the extended validity period. A Bidder may refuse the request without forfeiting its bid security. A Bidder granting the request shall not be required or permitted to modify its bid, except as provided in ITB 19.3. |
|  | In the case of fixed price contracts, if the award is delayed by a period exceeding fifty-six (56) days beyond the expiry of the initial bid validity, the Contract price shall be adjusted by a factor or factors specified in the request for extension. Bid evaluation shall be based on the Bid Price without taking into consideration the above correction. |
| Bid Security | The Bidder shall furnish as part of its bid, either a Bid-Securing Declaration or a bid security as specified in the BDS, in original form and in the amount specified in the BDS. A Bid-Securing Declaration shall use the form included in Section IV Bidding Forms. |
|  | If a bid security is specified pursuant to ITB 20.1, the bid security shall be a demand guarantee in any of the following forms at the Bidder’s option: - an unconditional guarantee issued by a bank or surety; - an irrevocable letter of credit; - a cashier’s or certified check; or - another security indicated in the BDS, - from a reputable source from an eligible country as specified in Section V-Eligibility criteria and social and environmental responsibility. If the unconditional guarantee is issued by an insurance company or a bonding company located outside the Employer’s Country, the issuer shall have a correspondent financial institution located in the Employer’s Country to make it enforceable. In the case of a bank guarantee, the bid security shall be submitted either using the Bid Security Form included in Section IV, Bidding Forms or in another substantially similar format approved by the Employer prior to bid submission. In either case, the form must include the complete name of the Bidder. The bid security shall be valid for twenty-eight days (28) beyond the original validity period of the bid, or beyond any period of extension if requested under ITB 19.2. |
|  | Any bid not accompanied by a substantially responsive bid security or Bid-Securing Declaration shall be rejected by the Employer as non-responsive. |
|  | The bid security of unsuccessful Bidders shall be returned as promptly as possible upon the successful Bidder’s furnishing of the performance security pursuant to ITB 42. |
|  | The bid security of the successful Bidder shall be returned as promptly as possible once the successful Bidder has signed the Contract and furnished the required performance security. |
|  | The bid security may be forfeited or the Bid-Securing Declaration executed: - if a Bidder withdraws its bid during the period of bid validity specified by the Bidder on the Letter of Bid or - if the successful Bidder fails to: #### sign the Contract in accordance with ITB 41; or #### furnish a performance security in accordance with ITB 42. |
|  | The Bid Security or the Bid Securing Declaration of a JV shall be in the name of the JV that submits the bid. If the JV has not been legally constituted into a legally enforceable JV at the time of bidding, the Bid Security or the Bid Securing Declaration shall be in the names of all future partners as named in the letter of intent referred to in ITB 4.1 and ITB 11.1. If a bid security is not required in the BDS pursuant to ITB 20.1, and (a) if a Bidder withdraws its bid during the period of bid validity specified by the Bidder on the Letter of Bid or any extension thereto provided by the Bidder, or (b) if the successful Bidder fails to: sign the Contract in accordance with ITB 41; or furnish a performance security in accordance with ITB 42; - the Borrower may, if provided for in the BDS, declare the Bidder disqualified to be awarded a contract by the Employer for a period of time as stated in the BDS. |
| Format and Signing of Bid | The Bidder shall prepare one original of the documents comprising the bid as described in ITB 11 and clearly mark it “Original.” Alternative bids, if permitted in accordance with ITB 13, shall be clearly marked “Alternative”. In addition, the Bidder shall submit copies of the bid, in the number specified in the BDS and clearly mark them “Copy.” In the event of any discrepancy between the original and the copies, the original shall prevail. |
|  | The original and all copies of the bid shall be typed or written in indelible ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall consist of a written confirmation as specified in the BDS and shall be attached to the bid. The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the bid where entries or amendments have been made shall be signed or initialed by the person signing the bid. |
|  | In case the Bidder is a JV, the Bid shall be signed by an authorized representative of the JV on behalf of the JV, and so as to be legally binding on all the members as evidenced by a power of attorney signed by their legally authorized representatives. Any interlineations, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the bid. |
|  | Submission and Opening of Bids |
| Submission, Sealing and Marking of Bids | The Bidder shall enclose the original and all copies of the bid, including alternative bids, if permitted in accordance with ITB 13, in separate sealed envelopes, duly marking the envelopes as “Original”, “Alternative” and “Copy.” These envelopes containing the original and the copies shall then be enclosed in one single envelope. |
|  | The inner and outer envelopes shall: - bear the name and address of the Bidder; - be addressed to the Employer in accordance with ITB 23.1; - bear the specific identification of this bidding process indicated in accordance with ITB 1.1; and - bear a warning not to open before the time and date for bid opening. |
|  | If all envelopes are not sealed and marked as required, the Employer will assume no responsibility for the misplacement or premature opening of the bid. |
| Deadline for Submission of Bids | Bids must be received by the Employer at the address and no later than the date and time indicated in the BDS. When so specified in the BDS, bidders shall have the option of submitting their bids electronically. Bidders submitting bids electronically shall follow the electronic bid submission procedures specified in the BDS. |
|  | The Employer may, at its discretion, extend the deadline for the submission of bids by amending the Bidding Document in accordance with ITB 8, in which case all rights and obligations of the Employer and Bidders previously subject to the deadline shall thereafter be subject to the deadline as extended. |
| Late Bids | The Employer shall not consider any bid that arrives after the deadline for submission of bids, in accordance with ITB 23. Any bid received by the Employer after the deadline for submission of bids shall be declared late, rejected, and returned unopened to the Bidder. |
| Withdrawal, Substitution, and Modification of Bids | A Bidder may withdraw, substitute, or modify its bid after it has been submitted by sending a written notice, duly signed by an authorized representative, and shall include a copy of the authorization in accordance with ITB 21.2. The corresponding substitution or modification of the bid must accompany the respective written notice. All notices must be: - prepared and submitted in accordance with ITB 21 and ITB 22 (except that withdrawals notices do not require copies), and in addition, the respective envelopes shall be clearly marked “Withdrawal,” “Substitution,” “Modification;” and - received by the Employer prior to the deadline prescribed for submission of bids, in accordance with ITB 23. |
|  | Bids requested to be withdrawn in accordance with ITB 25.1 shall be returned unopened to the Bidders. |
|  | No bid may be withdrawn, substituted, or modified in the interval between the deadline for submission of bids and the expiration of the period of bid validity specified by the Bidder on the Letter of Bid or any extension thereof. |
| Bid Opening | Except in the cases specified in ITB 24 and 25, the Employer shall publicly open and read out in accordance with ITB 26 all bids received by the deadline (regardless of the number of bids received), at the date, time and place specified in the BDS, in the presence of Bidders` designated representatives and anyone who choose to attend. Any specific electronic bid opening procedures required if electronic bidding is permitted in accordance with ITB 23.1, shall be as specified in the BDS. |
|  | First, envelopes marked “Withdrawal” shall be opened and read out and the envelope with the corresponding bid shall not be opened, but returned to the Bidder. No bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at bid opening. Next, envelopes marked “Substitution” shall be opened and read out and exchanged with the corresponding bid being substituted, and the substituted bid shall not be opened, but returned to the Bidder. No bid substitution shall be permitted unless the corresponding substitution notice contains a valid authorization to request the substitution and is read out at bid opening. Envelopes marked “Modification” shall be opened and read out with the corresponding bid. No bid modification shall be permitted unless the corresponding modification notice contains a valid authorization to request the modification and is read out at bid opening. Only bids that are opened and read out at bid opening shall be considered further. |
|  | All other envelopes shall be opened one at a time, reading out: the name of the Bidder and the Bid Price(s), including any discounts and alternative bids, and indicating whether there is a modification; the presence or absence of a bid security or Bid-Securing Declaration; and any other details as the Employer may consider appropriate. Only discounts and alternative bids read out at bid opening shall be considered for evaluation. The Letter of Bid and the Schedules are to be initialed by a minimum of three representatives of the Employer attending bid opening. The Employer shall neither discuss the merits of any bid nor reject any bid (except for late bids, in accordance with ITB 24.1). |
|  | The Employer shall prepare a record of the bid opening that shall include, as a minimum, for each bid: the name of the Bidder and whether there is a withdrawal, substitution, or modification; the Bid Price, per lot if applicable, including any discounts and alternative bids; and the presence or absence of a bid security or a Bid-Securing Declaration. The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Bidders. |
|  | Evaluation and Comparison of Bids |
| Confidentiality | Information relating to the examination, evaluation and comparison of the bids, and qualification of the Bidders, and recommendation of contract award, shall not be disclosed to Bidders or any other persons not officially concerned with such process until information on Contract award is communicated to all Bidders in accordance with ITB 40. |
|  | Any attempt by a Bidder to influence the Employer in the examination, evaluation and comparison of the bids and qualification of the Bidders, or Contract award decisions may result in the rejection of its bid. |
|  | Notwithstanding ITB 27.2, from the time of bid opening to the time of Contract award, if any Bidder wishes to contact the Employer on any matter related to the bidding process, it should do so in writing. |
| Clarification of Bids | To assist in the examination, evaluation, and comparison of the bids, and qualification of the Bidders, the Employer may, at its discretion, ask any Bidder for a clarification of its bid. Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing. No change, including any voluntary increase or decrease in the prices and substance of the bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the bids, in accordance with ITB 32. |
|  | If a Bidder does not provide clarifications of its bid by the date and time set in the Employer’s request for clarification, its bid may be rejected. |
| Deviations, Reservations, and Omissions | During the evaluation of bids, the following definitions apply: (a) “Deviation” is a departure from the requirements specified in the Bidding Document; (b) “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the Bidding Document; and (c) “Omission” is the failure to submit part or all of the information or documentation required in the Bidding Document. |
| Determination of Responsiveness | The Employer’s determination of a bid’s responsiveness is to be based on the contents of the bid itself, as defined in ITB11. |
|  | A substantially responsive bid is one that meets the requirements of the Bidding Document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that, - if accepted, would: #### affect in any substantial way the scope, quality, or performance of the Plant and Installation Services specified in the Contract; or #### limit in any substantial way, inconsistent with the Bidding Document, the Employer’s rights or the Bidder’s obligations under the proposed Contract; or - if rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive bids. |
|  | The Employer shall examine the technical aspects of the bid in particular, to confirm that all requirements of Section VII, Employer’s Requirements have been met without any material deviation, reservation, or omission. |
|  | If a bid is not substantially responsive to the requirements of the Bidding Document, it shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. |
| Nonmaterial Nonconformities | Provided that a bid is substantially responsive, the Employer may waive any nonconformity in the bid that does not constitute a material deviation, reservation or omission. |
|  | Provided that a bid is substantially responsive, the Employer may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the bid related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the price of the bid. Failure of the Bidder to comply with the request may result in the rejection of its bid. |
|  | Provided that a bid is substantially responsive, the Employer shall rectify quantifiable nonmaterial nonconformities related to the Bid Price. To this effect, the Bid Price shall be adjusted, for comparison purposes only, to reflect the price of a missing or non-conforming item or component. |
| Correction of Arithmetical Errors | Provided that the bid is substantially responsive, the Employer shall correct arithmetical errors on the following basis: - where there are errors between the total of the amounts given under the column for the price breakdown and the amount given under the Total Price, the former shall prevail and the latter will be corrected accordingly; - where there are errors between the total of the amounts of Schedule Nos. 1 to 4 and the amount given in Schedule No. 5 (Grand Summary), the former shall prevail and the latter will be corrected accordingly; and - if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above. |
|  | The Bidder shall be requested to accept correction of arithmetical errors. Failure to accept the correction in accordance with ITB 32.1 shall result in the rejection of the Bid. |
| Conversion to Single Currency | For evaluation and comparison purposes, the currency(ies) of the bid shall be converted into a single currency as specified in the BDS. |
| Margin of Preference | No margin of domestic preference shall apply. |
| Evaluation of Bids | The Employer shall use the criteria and methodologies indicated in this Clause. No other evaluation criteria or methodologies shall be permitted. Technical Evaluation The Employer will carry out a detailed technical evaluation of the bids not previously rejected to determine whether the technical aspects are in compliance with the Bidding Document. The bid that does not meet minimum acceptable standards of completeness, consistency and detail, and the specified minimum (or maximum, as the case may be) requirements for specified functional guarantees, will be rejected for non-responsiveness. In order to reach its determination, the Employer will examine and compare the technical aspects of the bids on the basis of the information supplied by the bidders, taking into account the following: (a) overall completeness and compliance with the Employer’s Requirements; conformity of the Plant and Installation Services offered with specified performance criteria, including conformity with the specified minimum (or maximum, as the case may be) requirement corresponding to each functional guarantee, as indicated in the Specification and in Section III Evaluation and Qualification Criteria; suitability of the Plant and Installation Services offered in relation to the environmental and climatic conditions prevailing at the site; and quality, function and operation of any process control concept included in the bid; (b) type, quantity and long-term availability of mandatory and recommended spare parts and maintenance services; and (c) other relevant factors, if any, listed in Section III, Evaluation and Qualification Criteria. Where alternative technical solutions have been allowed in accordance with ITB 13, and offered by the Bidder, the Employer will make a similar evaluation of the alternatives. Where alternatives have not been allowed but have been offered, they shall be ignored. |
|  | Economic Evaluation To evaluate a bid, the Employer shall consider the following: - the bid price, excluding provisional sums and the provision, if any, for contingencies in the Price Schedules; - price adjustment for correction of arithmetic errors in accordance with ITB 32.1; - price adjustment due to discounts offered in accordance with ITB17.11; - price adjustment due to quantifiable nonmaterial nonconformities in accordance with ITB 31.3; - converting the amount resulting from applying (a) to (c) above, if relevant, to a single currency in accordance with ITB 33; and - the additional evaluation factors indicated in Section III, Evaluation and Qualification Criteria. |
|  | If price adjustment is allowed in accordance with ITB 17.7, the estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in bid evaluation. |
|  | If this Bidding Document allows Bidders to quote separate prices for different lots (contracts), and the award to a single Bidder of multiple lots (contracts), the methodology to determine the lowest evaluated price of the lot (contract) combinations, including any discounts offered in the Letter of Bid, is specified in Section III, Evaluation and Qualification Criteria. |
|  | If the bid, which results in the lowest Evaluated Bid Price, is significantly lower than the Employer’s estimation or seriously unbalanced or front loaded in the opinion of the Employer, the Employer may require the Bidder to produce detailed price analyses for any or all items of the Price Schedules, to demonstrate the internal consistency of those prices with the methods and time schedule proposed. If it turns out that the bid price is abnormally low, the bid may be declared non-compliant and rejected. After evaluation of the price analyses, taking into consideration the terms of payments, the Employer may require that the amount of the performance security be increased at the expense of the Bidder to a level sufficient to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract. |
| Comparison of Bids | The Employer shall compare all substantially responsive bids in accordance with ITB 35.4 to determine the lowest evaluated bid. |
| Eligibility and Qualification of the Bidder | The Employer shall determine to its satisfaction whether the Bidder that is selected as having submitted the lowest evaluated and substantially responsive bid either continues to meet (if prequalification applies) or meets (if post-qualification applies) the qualifying criteria specified in Section III, Evaluation and Qualification Criteria. |
|  | The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 15. An affirmative determination shall be a prerequisite for award of the Contract to the Bidder. A negative determination shall result in disqualification of the bid, in which event the Employer shall proceed to the next lowest evaluated bid to make a similar determination of that Bidder’s qualifications to perform satisfactorily. The capabilities of the manufacturers and subcontractors proposed in its Bid to be used by the lowest evaluated Bidder for identified major items of supply or services will also be evaluated for acceptability in accordance with Section III, Evaluation and Qualification Criteria. Their participation should be confirmed with a letter of intent between the parties, as needed. Should a manufacturer or subcontractor be determined to be unacceptable, the Bid will not be rejected, but the Bidder will be required to substitute an acceptable manufacturer or subcontractor without any change to the bid price. Prior to signing the Contract, the corresponding Appendix to the Contract Agreement shall be completed, listing the approved manufacturers or subcontractors for each item concerned. |
| Employer’s Right to Accept Any Bid, and to Reject Any or All Bids | The Employer reserves the right to accept or reject any bid, and to annul the bidding process and reject all bids at any time prior to contract award, without thereby incurring any liability to Bidders. In case of annulment, all bids submitted and specifically, bid securities, shall be promptly returned to the Bidders. |
|  | Award of Contract |
| Award Criteria | Subject to ITB 38.1, the Employer shall award the Contract to the Bidder whose offer has been determined to be the lowest evaluated bid and is substantially responsive to the Bidding Document, provided further that the Bidder is determined to be eligible and qualified to perform the Contract satisfactorily. |
| Notification of Award | Prior to the expiration of the period of bid validity, the Employer shall notify the successful Bidder, in writing, that its bid has been accepted. The notification letter (hereinafter and in the Conditions of Contract and Contract Forms called the “Letter of Acceptance”) shall specify the sum that the Employer will pay the Contractor in consideration of the execution and completion of the Plant and Installation Services (hereinafter and in the Conditions of Contract and Contract Forms called “the Contract Price”). At the same time, the Employer shall also notify all other Bidders of the results of the bidding. |
|  | Until a formal contract is prepared and executed, the notification of award shall constitute a binding Contract. |
|  | The Employer shall promptly respond in writing to any unsuccessful Bidder who, after notification of award in accordance with ITB 40.2, requests in writing the grounds on which its bid was not selected. |
| Signing of Contract | Promptly upon notification, the Employer shall send the successful Bidder the Contract Agreement. |
|  | Within twenty-eight (28) days of receipt of the Contract Agreement, the successful Bidder shall sign, date, and return it to the Employer. |
|  | Notwithstanding ITB 41.2 above, in case signing of the Contract Agreement is prevented by any export restrictions attributable to the Employer, to the country of the Employer, or to the use of the Plant and Installation Services to be supplied, where such export restrictions arise from trade regulations from a country supplying those Plant and Installation Services, the Bidder shall not be bound by its bid, always provided, however, that the Bidder can demonstrate to the satisfaction of the Employer and of the Agency that signing of the Contact Agreement has not been prevented by any lack of diligence on the part of the Bidder in completing any formalities, including applying for permits, authorizations and licenses necessary for the export of the Plant and Installation Services under the terms of the Contract. |
| Performance Security | Within twenty-eight (28) days of the receipt of notification of award from the Employer, the successful Bidder shall furnish the performance security in accordance with the General Conditions, subject to ITB 35.7, using for that purpose the Performance Security Form included in Section X, Contract Forms, or another form acceptable to the Employer. If the performance security furnished by the successful Bidder is in the form of a bond, it shall be issued by a bonding or insurance company that has been determined by the successful Bidder to be acceptable to the Employer. A foreign institution providing a bond shall have a correspondent financial institution located in the Employer’s Country. |
|  | Failure of the successful Bidder to submit the above-mentioned Performance Security or sign the Contract shall constitute sufficient grounds for the annulment of the award and forfeiture of the bid security or execution of the Bid-Securing Declaration. In that event the Employer may award the Contract to the next lowest evaluated Bidder whose offer is substantially responsive and is determined by the Employer to be qualified to perform the Contract satisfactorily. |

| Section II. Bid Data Sheet |  |
| --- | --- |
| A. Introduction |  |
| ITB 1.1 | The number of the Invitation for Bids is : KETRACO/ST/007/2024 |
| ITB 1.1 | The Employer is: Kenya Electricity Transmission Company Limited |
| ITB 1.1 | The name of the ICB is: EPC Construction for the pilot digital 400/132kV Makindu Substation The identification number of the ICB is: KETRACO/ST/007/2024 |
| ITB 2.1 | The name of the Project is: EPC Construction for the pilot digital 400/132kV Makindu Substation |
| ITB 4.1 (b) | Maximum number of members in the JV shall be: Two (2) |
| B. Bidding Document |  |
| ITB 7.1 | For clarification purposes only, the Employer’s address is: Attention: Senior Manager Supply Chain Kenya Electricity Transmission Company Limited Kawi Complex, Block B Off Popo Road, Off Red Cross Road, South C P O Box 34942 - 00100 Nairobi Tel : +254-020-4956000 +254-719-018000 Email: makinduprocurement@ketraco.co.ke |
| ITB 7.1 | Web page: www.ketraco.co.ke |
| ITB 7.4 | A Pre-Bid meeting shall take place at the following date, time and place: Date: 11th September 2024 Time: 10:00 am EAT Place: Kawi Complex, Block B Thereafter, a site visit shall be held by the Employer at the following date, time and place: Date: 12th September 2024 Time: 11:00 am EAT Place: Makindu substation site The Bidders shall cover their own expenses for site visit. KETRACO encourages all bidders to attend the pre-bid meeting and site visits. |
| C. Preparation of Bids |  |
| ITB 10.1 | The language of the bid is: English |
| ITB 11.1 (l) | The Bidder shall submit with its bid the following additional documents: - All Technical Schedules with detailed information of offered materials and equipment, in which all required information, shall be filled completely as specified in the Tender documents. - Copies of Type Test Reports and technical documents (catalogues, brochures, drawings) of each major equipment offered shall form part of the bid. Copies of Type Test Reports shall meet the following requirements: - Type test reports shall be carried out by a laboratory independent from the manufacturer or with the witness of an independent laboratory. Accreditation certificate for the testing laboratory shall be presented. - Results of type tests shall have been conducted within the last five years prior to the date of tender submission. The bidder shall submit contact details (Title, email and fax) of certifying laboratory. - Testing materials and equipment in Type Test Reports shall have the same code/ country/ manufacturer and technical parameters as offered materials and equipment. Type tests of non-conforming materials/equipment shall not be accepted. - Type test reports shall include all items tested and results confirming that they meet the requirements of applied standards as stipulated in Tender Documents. - The following information shall be submitted for equipment manufacturers: - Quality Management System Manual and ISO 9001 certification of the equipment manufacturer or other internationally recognized equivalent. - ISO 45001(Occupational Health and Safety) certification of the equipment manufacturer or other internationally recognized equivalent. - Catalogues, literature, and supply reference lists of proposed equipment - Equipment general arrangement drawings - Duly signed manufacturer’s authorization form from the major and additional equipment manufacturers in accordance with Section IV: Bidding Forms. The major equipment are: - Power transformers - Conductors - OPGW and Termination Equipment - Earth wire - High Voltage, Medium Voltage and Low Voltage Switchgear (Circuit Breakers, Disconnectors and Earth Switches) - Instrument Transformers - Surge Arrestors - Control And Protection Equipment (Relays, BCUs, PMUs, MUs, SCUs, Meters, AVRs) - Substation Automation System - Communication System - Diesel Generator - Substation Auxiliary Transformer - Insulators The additional equipment are: - Galvanised Steel Structures (Gantries, Equipment Supports and Towers) - Hardware fittings - MV & LV Cables - Firefighting and fire alarm systems - Low Voltage system |
| ITB 13.1 | Alternative bids are not permitted. |
| ITB 13.2 | Alternatives to the Time Schedule are not permitted. |
| ITB 13.4 | Not applicable. |
| ITB 17.5(a) | Named place of destination is: The project site in Makindu |
| ITB 17.5(d) | Named place of final destination is: The project site in Makindu |
| ITB 17.5(d) | Taxes, duties and fees exemptions, to which payments under the Contract are entitled, are specified in clause 14.1 (b) of the Particular Conditions of Contract. |
| ITB 17.7 | The prices quoted by the Bidder shall be fixed and firm. |
| ITB 18.1 | The currency(ies) of the bid shall be as follows: The rates and prices shall be quoted by the Bidder in the Schedules separately in the following currencies: - for those inputs to the Plant and Installation services that the Bidder expects to supply from within the Employer’s country, in Kenya Shillings, and further referred to as “the local currency”; and - for those inputs to the Plant and Installation services that the Bidder expects to supply from outside the Employer’s country (referred to as “the foreign currency requirements”), in Euros (EUR) or US Dollars (USD). - for the services of design and the assembly, the prices will be quoted in foreign currency (limited to Euros (EUR) or US Dollars (USD)) and/or in the currency of the country of the Employer according to the currency in which the costs are incurred. |
| ITB 19.1 | The bid validity period shall be 180 days. |
| ITB 20.1 | Bids shall be accompanied by a bid security in an amount of not less than EUR 700,000, issued by a recognized Kenyan bank as per the Form of Bid Security included in Section IV – Bidding Forms - Form of Bid Security (Bank Guarantee). The bid security shall be valid for 28 days beyond the original validity period of 180 days, or 28 days beyond any period of extension if required under ITB 19.2 |
| ITB 20.3 (d) | Other types of acceptable securities: None |
| ITB 20.9 | If the Bidder incurs any of the actions prescribed in subparagraphs (a) or (b) of this provision, the Borrower will declare the Bidder ineligible to be awarded contracts by the Employer for a period of three (3) years. |
| ITB 21.1 | In addition to the original of the bid, the number of copies is: Three (3) hard copies and Two (2) soft copies in flash disks. The soft copies shall contain the full bid including an editable excel version of the filled-in Schedules of Rates and Prices and an editable word version of the filled-in Technical Data sheets/ Technical Schedules. The soft copies shall be structured strictly as per the hardcopies. Each part (Part 1, 2 and 3) shall be presented in a separate folder. Each Section shall be provided as single PDF files named as per ITB and BDS clause 11.1. Drawings must also be provided in at least A3 size. |
| ITB 21.2 | The written confirmation of authorization to sign on behalf of the Bidder shall consist of: A power of attorney established in the name of the signatory of the bid. |
| D. Submission and Opening of Bids |  |
| ITB 23.1 | For bid submission purposes only, the Employer’s address is: Attention: Senior Manager Supply Chain Kenya Electricity Transmission Company Limited Second Floor, Kawi Complex, Block B Off Popo Road, Off Red Cross Road, South C P O Box 34942 - 00100 Nairobi The deadline for bid submission is: Date: 25th October 2024 Time: 10:00 am EAT Bidders shall not have the option of submitting their bids electronically. |
| ITB 26.1 | The bid opening shall take place at: Kenya Electricity Transmission Company Limited Kawi Complex, Block B Off Popo Road, Off Red Cross Road, South C P O Box 34942 - 00100 Nairobi Date: 25th October 2024 Time: Immediately after the deadline for bid submission No minimum number of bids is required in order to proceed to bid opening. |
| E. Evaluation, and Comparison of Bids |  |
| ITB 33.1 | The currency(ies) of the Bid shall be converted into a single currency as follows: The currency that shall be used for bid evaluation and comparison purposes to convert all bid prices expressed in various currencies into a single currency is: Kenya Shilling The source of exchange rate shall be: The Central Bank of Kenya The date for the exchange rate shall be: twenty-eight (28) days prior to Bid submission The Employer will convert the amounts in various currencies in which the Bid Price, corrected pursuant to Clause 32, is payable to the single currency identified above at the selling rates established for similar transactions by the authority specified and on the date stipulated above. |

Section III. Evaluation and Qualification Criteria (Following Prequalification)

This Section contains all the criteria that the Employer shall use to evaluate bids and qualify Bidders.  In accordance with ITB 35 and ITB 37, no other factors, methods or criteria shall be used. The Bidder shall provide all the information requested in the forms included in Section IV, Bidding Forms.

Wherever a Bidder is required to state a monetary amount, Bidders should indicate the USD equivalent using the rate of exchange determined as follows:

-For construction turnover or financial data required for each year - Exchange rate prevailing on the last day of the respective calendar year.

-Value of single contract - Exchange rate prevailing on the date of the contract.

Exchange rates shall be taken from the publicly available source identified in the ITB 33.1. Any error in determining the exchange rates in the Bid may be corrected by the Employer.

1.	Evaluation

1.1	Technical Evaluation

In addition to the criteria listed in ITB 35.2 (a) – (c) the following factors shall apply:

The assessment of the Technical Proposal submitted by a Bidder shall comprise

- evaluation of the Bidder’s technical capacity to mobilize key equipment and key personnel to carry out the works

- construction method

- construction schedule

- Sufficiently detailed supply sources, in accordance with requirements specified in Section VII – Employer’s Requirements.

1.2	Economic Evaluation

The following factors and methods will apply:

(a)	Time Schedule:

Time to complete and commission the Plant and Installation Services from the effective date specified in Article 3 of the Contract Agreement is 20 Months; with time for completion of pre-commissioning activities being 18 months and time for commissioning being 2 months. No credit will be given for earlier completion and commissioning. Proposals with schedules above 20 months will be rejected.

(b)	Functional Guarantees of the Plant and Installation Services

The evaluation will be based on the losses indicated by the Contractor in the Guaranteed Technical Schedules.

The total capitalized cost of the losses will be added to the cost of transformers for comparing bids.

The cost of guaranteed power transformer no-load and load losses will be added to the transformer price, and the evaluated transformer cost will be calculated as per the following formula:

CTev = CT + (Ln x CLn) + (LL x CLL)

Where:

- CTev  = The evaluated cost of the transformer;

- CT   = The cost of the transformer as indicated in the Schedule of Rates and Prices;

- Ln  =  The no-load losses in kW, as indicated in the Schedule of Guaranteed Technical Characteristics;

- LL  =  The load losses in kW, at continuous maximum rating, as indicated in the Schedule of Guaranteed Technical Characteristics;

- CLn  = The cost per kW of no-load losses, that is 900,000 KES/kW;

- CLL  = The cost per kW of load losses, that is, 500,000 KES/kW.

(c) Specific additional criteria

The evaluation method, shall be as follows:

  - Evaluating transformer rating.

|  | Description | Required | For the purposes of evaluation an adjustment as calculated below will be added to the tender price. |
| --- | --- | --- | --- |
| 1. | 400/132kV Power Transformer - Rated power at site conditions (ONAF1/ONAF2) | 90 MVA | Transformers with a rated power less than 2.5% of the required power rating will be rejected. KSh 40,000/KVA for one percent (1%) or pro-rata for less than one percent drop in the above figure. |
| 2. | 11/0.415kV Auxiliary Transformer - Rated power at site conditions | 500 kVA |  |
| 3. | 400/132kV Power Transformer losses | - Maximum no load losses: 80 KW - Maximum load losses at 75°C and rated frequency: - ONAF rated power (90MVA) and principal tapping- to be proved by test and calculation: 240 (Max) at 90MVA Base - ONAN rated power (75MVA) and principal tapping- to be proved and calculation: 180 (Max) 75 MVA Base - Maximum Auxiliary Power 6 KW | Transformers with losses 2.5% above the required losses will be rejected After commissioning of transformers, in case of the tested load loss and no-load loss values differ from the guaranteed ones, the below penalties will be applied as liquidated damages: - No Load: USD 9,000 / kW - Load Loss: USD 4,000 / kW -Auxiliary Power: USD 4,000/kW |

Any adjustments in price that result from the above procedures shall be added, for purposes of comparative evaluation only, to arrive at an “Evaluated Bid Price.”  Bid prices quoted by bidders shall remain unaltered.

In reference to ITB 31.3 the Employer for evaluation purposes only, will add to the bid price the cost of quantifiable deviations and omissions from the Technical Specifications as identified in the bidding document. The adjustment shall be made by loading to the bidder the average price of the other substantially responsive bidders.

Loaded Bid Price Value of omission = (P1+P2+P3+……+Pn)/n

Where n= number of substantially responsive bidders.

1.3	Technical alternatives

Technical alternatives are not permitted.

2.	Qualification

2.1	Update of Information

The Bidder and any subcontractors shall meet or continue to meet the criteria used at the time of prequalification.

Bidders who were conditionally prequalified shall meet the conditions of their prequalification to the satisfaction of the Employer at the time of submitting their bids. Failure to comply will result in disqualification from the bidding process and their bids rejected as non-responsive.

2.2	Financial Resources – Not Applicable

Using the relevant Forms No FIN-3.3 and FIN-3.4 in Section IV, Bidding Forms, the Bidder must demonstrate access to, or availability of, financial resources such as liquid assets, unencumbered real assets, lines of credit, and other financial means, other than any contractual advance payments to meet:

(i) the following cash-flow requirement:

and

(ii) the overall cash flow requirements for this contract and its current works commitment.

2.3	Personnel

The Bidder must demonstrate that it will have the personnel for the key positions that meet the following requirements:

| No. | Position | Total Work Experience (years) | Experience In Similar Work (years) | Minimum Qualifications |
| --- | --- | --- | --- | --- |
| P1 | Project Manager - - To be stationed in the Contractor’s Project office in Kenya dedicated to the project. | 15 | At least three (3) completed projects in similar position in the last ten (10) years | - Bachelor’s Degree in Electrical, Mechanical, Civil Engineering or equivalent - Valid license to practice engineering as a professional engineer in country of origin or residence |
| P2 | Construction Manager - To be stationed in the Site office in Kenya dedicated to the project. | 10 | At least two (2) completed substation and line projects in similar position in the last seven (7) years | - Bachelor’s Degree in Civil, Electrical Engineering or equivalent - Valid license to practice engineering as a professional engineer in country of origin or residence |
| P3 | Substation Electrical Engineer | 10 | At least two (2) completed substation projects in similar position in the last seven (7) years | - Bachelor’s Degree in Electrical Engineering or equivalent - Valid license to practice engineering as a professional engineer in country of origin or residence |
| P4 | Control and Protection Engineer | 10 | At least two (2) completed substation projects in similar position in the last seven (7) years | - Bachelor’s Degree in Electrical Engineering or equivalent - Valid license to practice engineering as a professional engineer in country of origin or residence |
| P5 | Civil/Structural Engineer | 10 | At least two (2) completed substation projects in similar position in the last seven (7) years | - Bachelor’s Degree in Civil Engineering or equivalent - Valid license to practice engineering as a professional engineer in country of origin or residence |
| P6 | Transmission Line Engineer | 10 | At least two (2) completed line projects in similar position in the last seven (7) years | - Bachelor’s Degree in Civil Engineering or equivalent - Valid license to practice engineering as a professional engineer in country of origin or residence |
| P7 | Communications Expert | 10 | At least two (2) completed substation projects in similar position in the last seven (7) years | - Bachelor’s Degree in Electrical Engineering or equivalent - Valid license to practice engineering as a professional engineer in country of origin or residence |
| P8 | Commissioning Engineer | 10 | At least two (2) completed substation projects in similar position in the last seven (7) years | - Bachelor’s Degree in Electrical Engineering or equivalent - Valid license to practice engineering as a professional engineer in country of origin or residence |
| P9 | SCADA Systems Expert | 10 | At least two (2) completed substation projects in similar position in the last seven (7) years | - Bachelor’s Degree in Electrical Engineering or equivalent - Valid license to practice engineering as a professional engineer in country of origin or residence |
| P10 | Environmental, Health & Safety Specialist - To be stationed in the Site office in Kenya dedicated to the project. | 7 | At least one (1) completed substation projects in similar position in the last seven (5) years | Diploma in any technical field with training in Safety, Health and Environment |
| P11 | Social Safeguards Specialist | 7 | At least one (1) completed substation projects in similar position in the last seven (5) years | Diploma or course that has social and environmental and safeguards assessment |
| P12 | Quality Control Specialist | 7 | At least one (1) completed substation projects in similar position in the last five (5) years |  |
| P13 | Gender Based Violence (GBV)/ Sexual Exploitation and Abuse (SEA) and Sexual Harassment (SH) Expert | 5 | 3 years experience |  |
| P14 | Scheduler | 10 | At least one (1) completed substation projects in similar position in the last seven (7) years |  |

The Bidder shall provide details of the proposed personnel and their experience records in the relevant Information Forms (PER-1 and PER-2) included in Section IV, Bidding Forms.

2.4	Equipment

The Bidder must demonstrate that it will have access to the key Contractor’s equipment listed hereafter:

| No. | Equipment Type and Characteristics | Minimum Number required |
| --- | --- | --- |
|  | A. Substation Work |  |
| 1 | Pickup truck | 3 |
| 2 | 2 or 4-wheel drive utility vehicle | 2 |
| 3 | Lorry up to 10 tones | 2 |
| 4 | Lorry over 10 tones | 1 |
| 5 | Excavator/tractor/JCB | 1 |
| 6 | Foundation gang tools and plant | 2 |
| 7 | Crane up to 40 tonnes | 1 |
| 8 | Three phase secondary injection test kit-OMICRON 356/256 | 1 |
| 9 | CPC 100 Primary test Universe kit | 1 |
| 10 | OMICRON DANEO 400, Network test | 1 |
| 11 | OMICRON Station Scout, Automation test 60 | 1 |
| 12 | Mobile Concrete batching plant | 1 |
| 13 | Tensioner and puller machines for the relevant conductor size and tools | 1 |
| 14 | Earth resistance Test Kit | 1 |
| 15 | Diesel generator | 1 |
| 16 | SF6 gas handling equipment | 1 |
| 17 | Oil Purifier and Vacuum Machine ( at least 4000l/hour) | 1 |
|  | B. Transmission Line Work |  |
| 1 | Conductor Puller and Tensioner Machine | 1 |
| 2 | Hydraulic Crimping Tools | 5 |
| 3 | Concrete mixer | 4 |
| 4 | Lorry (4-8 ton) | 4 |
| 5 | Tower erection equipment in line with construction methodology | 4 |
| 6 | Excavator (0.3m3 of Larger) or JCB | 1 |
| 7 | OPGW jointing tools | 1 |
| 8 | Engine winch | 3 |
| 9 | OTDR test | 1 |
| 10 | CME’s for 400 kV | 2 pairs |
| 11. | CME’s for 400 kV | 2 pairs |

The Bidder shall provide further details of proposed items of equipment using the Form EQU in Section IV.

2.5 	Subcontractors/manufacturers

Subcontractors/manufacturers for the following major items of supply or services must meet the following minimum criteria, herein listed for that item:

| S/No | Description of Item | Minimum Criteria to be met by Manufacturers | Submission Requirement |
| --- | --- | --- | --- |
| 1. | 400kV Switchyard equipment | - 15 years manufacturing experience of 400kV or above of switchyard equipment. - 400kV Switchyard equipment being in successful operation for at least 7 years. The operational experience shall be supported by end-user certificates/letters from at least three (3) utilities/clients with comprehensive contact details. - Supply of 400kV switchyard equipment to at least five (5) project sites of which shall be outside the manufacturer’s home country, supported by end-user certificates/letters from the utilities/clients with comprehensive contact details. | - Supply record - Outline drawing, - type test certificates issued by independent institution and less than 5 years old, - Quality Assurance manual, - ISO 9001 certificate or equivalent - end-user certificates/letters from the utilities/clients |
| 2. | 132kV switchyard equipment | - 15 years manufacturing experience of 132kV or above of switchyard equipment - 132kV Switchyard equipment being in successful operation for at least 7 years. The operational experience shall be supported by end-user certificates/letters from at least three (3) utilities/clients with comprehensive contact details. - Supply of 132kV switchyard equipment to at least five (5) project sites of which shall be outside the manufacturer’s home country, supported by end-user certificates/letters from the utilities/clients with comprehensive contact details. | - Supply record - Outline drawing, - type test certificates issued by independent institution and less than 5 years old, - Quality Assurance manual, - ISO 9001 certificate or equivalent - end-user certificates/letters from the utilities/clients |
| 3. | Power/Auto Transformers | - 20 years of manufacturing experience of power transformers of rating 400/132kV, minimum 90MVA. - Power Transformers being in successful operation for at least 15 years. The operational experience shall be supported by end-user certificates/letters from at least three (3) utilities/clients with comprehensive contact details. - Supply of 400/132kV Power Transformers to at least five (5) project sites of which shall be outside the manufacturer’s home country, supported by end-user certificates/letters from the utilities/clients with comprehensive contact details. | - Supply record - Outline drawing, - type test certificates issued by independent institution and less than 5 years old, - Quality Assurance manual, - ISO 9001 certificate or equivalent - end-user certificates/letters from the utilities/clients - Short-circuit strength verification as per IEC-60076-5 for the Power Transformer, |
| 5. | Control and Protection System | - 15 years of manufacturing experience of control and protection systems. - Control and protection system being in successful operation for at least 10 years. The operational experience shall be supported by end-user certificates/letters from at least three (3) utilities/clients with comprehensive contact details. - Supply of control and protection systems to at least three project sites of which shall be outside the manufacturer’s home country, supported by end-user certificates/letters from the utilities/clients with comprehensive contact details. | - Supply record - Outline drawing, - type test certificates issued by independent institution and less than 5 years old, - Quality Assurance manual, - ISO 9001 certificate or equivalent - end-user certificates/letters from the utilities/clients |
| 6. | Substation and Automation systems, and communication systems (SASCS) | - 15 years of manufacturing experience - SASCS being in successful operation for at least 5 years. The operational experience shall be supported by end-user certificates/letters from at least three (3) utilities/clients with comprehensive contact details. - Supply of SASCS to at least three (3) project sites of which shall be outside the manufacturer’s home country, supported by end-user certificates/letters from the utilities/clients with comprehensive contact details. | - Supply record - Outline drawing, - type test certificates issued by independent institution and less than 5 years old, - Quality Assurance manual, - ISO 9001 certificate or equivalent - end-user certificates/letters from the utilities/clients |
| 6. | 400 kV Transmission Line Towers | - 15 years of manufacturing experience - The tower manufacturer shall have supplied towers for at least two (2) projects at 400kV voltage level or above in the last ten (10) years. The operational experience shall be supported by end-user certificates/letters from at least one (1) utility/client with comprehensive contact details. | - Supply record - Outline drawing, - type test certificates issued by independent institution and less than 5 years old, - Quality Assurance manual, - ISO 9001 certificate or equivalent - end-user certificates/letters from the utilities/clients |

| S/no | Description of Item | Minimum Criteria to be met by Subcontractors | Submission Requirement |
| --- | --- | --- | --- |
| 1. | Local Civil Works Sub Contractor | The civil works local subcontractor shall be registered with National Construction Authority (NCA) of class two (NCA 2) category with proven experience in civil works contracts. Evidence of this eligibility must be provided at the bidding stage. Proof of successful registration shall be provided by the successful bidder upon commencement of the contract. Sub-contractor MUST have carried out foundation works in completed transmission projects in the last five (5) years. Experience must be supported with completion certificates and/or end-user testimonials/references/letters with comprehensive contact details of the end-user. | - Experience record - ISO 9001 and 45001 certificates or equivalent - Completion certificates and/or end-user testimonials/references |
| 2. | Local Electromechanical works subcontractor | The electromechanical works local subcontractor shall have class two (NCA 2) contractor license in electromechanical works issued by the National Construction Authority (NCA). Evidence of this eligibility must be provided at the bidding stage. Proof of successful registration shall be provided by the successful bidder upon commencement of the contract. Electromechanical subcontractor MUST provide proven records for the last five (5) years on previous similar assignments for substation projects of 132kV and above. Experience must be supported with completion certificates and/or end-user testimonials/references/letters with comprehensive contact details of the end-user. | - Experience record - ISO 9001 and 45001 certificates or equivalent - Completion certificates and/or end-user testimonials/references |

Failure to comply with this requirement will result in the rejection of the subcontractor.

In the case of a Bidder who offers to supply and install major items of supply under the contract that the Bidder did not manufacture or otherwise produce, the Bidder shall provide the manufacturer’s authorization, using the form provided in Section IV, showing that the Bidder has been duly authorized by the manufacturer or producer of the related plant and equipment or component to supply and/or install that item in the Employer’s country. The Bidder is responsible for ensuring that the manufacturer or producer complies with the requirements of ITB 4 and 5 and meets the minimum criteria listed above for that item.

Section IV. Bidding Forms

Table of Forms

Letter of Bid	55

Letter of Bid – Single Stage Bidding	55

Statement of Integrity, Eligibility and Social and Environmental Responsibility	58

Schedules of Rates and Prices	62

Schedule No. 1.  Plant and Mandatory Spare Parts Supplied from Abroad	62

Schedule No. 2.  Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country	63

Schedule No. 3.  Design Services	64

Schedule No. 4.  Installation and Other Services	65

Schedule No. 5.  Grand Summary	66

Schedule No. 6.  Recommended Spare Parts	67

Price Adjustment	68

Technical Proposal	70

Site Organization	71

Method Statement	72

Mobilization Schedule	73

Construction Schedule	74

Plant	75

Contractor’s Equipment	77

Personnel	78

Proposed Subcontractors for Major Items of Plant and Installation Services	80

Others - Time Schedule	Error! Bookmark not defined.

Others – Commercial or contractual aspects of the bidding documents that the Bidder would like to discuss with the Employer during clarifications	Error! Bookmark not defined.

Bidders Qualification following Prequalification	81

Form FIN–3.3 Financial Resources	82

Form FIN–3.4 Current Contract Commitments / Works in Progress	83

Bidders Qualification without prequalification	84

Form ELI-1.1 Bidder Information Form	85

Form ELI-1.2 Bidder's JV Information Form	86

Form CON–2 Historical Contract Non-Performance, Pending Litigation and Litigation History	87

Form FIN–3.1 Financial Situation and Performance	89

Form FIN–3.2 Average Annual Construction Turnover	91

Form FIN–3.3 Financial Resources	92

Form FIN–3.4 Current Contract Commitments / Works in Progress	93

Form EXP-4.1 General Construction Experience	94

* See Section III Evaluation and Qualification Criteria – Sub Factor 4.1Form EXP-4.2(a) Specific Construction and Contract Management Experience	94

Form EXP-4.2(b) Construction Experience in Key Activities	97

Form of Bid Security (Bank Guarantee)	99

Form of Bid-Securing Declaration	100

Manufacturer’s Authorization	101

Letter of Bid

Letter of Bid – Single Stage Bidding

Date:

ICB No.:

Invitation for Bid No.:

To:  _______________________________________________________________________

We, the undersigned, declare that:

- We have examined and have no reservations to the Bidding Document, including Addenda issued in accordance with Instructions to Bidders (ITB) 8	;

- We have no conflict of interest in accordance with ITB 4;

- We have not been suspended nor declared ineligible by the Employer based on execution of a Bid Securing Declaration in the Employer’s country in accordance with ITB 4.4.

- We offer to _________________________, in conformity with the Bidding Document, the following Plant and Installation Services:

- The price of our Bid, excluding any discounts offered in item (d) below is the sum of:  _________________________,  (_____________), and __________________, (___________)

- The discounts offered and the methodology for their application are:

;

- Our bid shall be valid for a period of ____________________________ days from the date fixed for the bid submission deadline in accordance with the Bidding Document, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

- If our bid is accepted, we commit to obtain a performance security in accordance with the Bidding Document;

- We are not participating, as a Bidder or a subcontractor, in more than one bid in this bidding process in accordance with ITB 4.2, other than alternative bids submitted in accordance with ITB 13;

- We have paid, or will pay the following commissions, gratuities, or fees with respect to the bidding process or execution of the Contract:

| Name of Recipient | Address | Reason | Amount |
| --- | --- | --- | --- |

(If none has been paid or is to be paid, indicate “none.”)

- We understand that this bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed; and

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive.

- We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in any type of fraud and corruption.

Name of the Bidder*

Name of the person duly authorized to sign the Bid on behalf of the Bidder**

Title of the person signing the Bid

Signature of the person named above

Date signed ________________________________ day of _______________________, _____

*: In the case of the Bid submitted by joint venture specify the name of the Joint Venture as Bidder

**: Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid

Statement of Integrity, Eligibility and Social and Environmental Responsibility

Reference name of the bid or proposal: ___________________________________ (The "Contract")

To: ______________________________________________(The "Contracting Authority")

- We recognise and accept that Agence Française de Développement ("AFD") only finances projects of the Contracting Authority subject to its own conditions which are set out in the Financing Agreement which benefits directly or indirectly to the Contracting Authority. As a matter of consequence, no legal relationship exists between AFD and our company, our joint venture or our suppliers, contractors, subcontractors, consultants or subconsultants. The Contracting Authority retains exclusive responsibility for the preparation and implementation of the procurement process and performance of the contract. The Contracting Authority means the Purchaser, the Employer, the Client, as the case may be, for the procurement of goods, works, plants, consulting services or non-consulting services.

- We hereby certify that neither we nor any other member of our joint venture or any of our suppliers, contractors, subcontractors, consultants or subconsultants are in any of the following situations:

2.1) Being bankrupt, wound up or ceasing our activities, having our activities administered by the courts, having entered into receivership, reorganisation or being in any analogous situation arising from any similar procedure;

2.2) Having been:

a. convicted, within the past five years by a court decision, which has the force of res judicata in the country where the Contract is implemented, of fraud, corruption or of any other offense committed during a procurement process or performance of a contract (in the event of such conviction, you may attach to this Statement of Integrity supporting information showing that this conviction is not relevant in the context of this Contract);

b. subject to an administrative sanction within the past five years by the European Union or by the competent authorities of the country where we are constituted, for fraud, corruption or for any other offense committed during a procurement process or performance of a contract (in the event of such sanction, you may attach to this Statement of Integrity supporting information showing that this sanction is not relevant in the context of this Contract);

c. convicted, within the past five years by a court decision, which has the force of res judicata, of fraud, corruption or of any other offense committed during the procurement process or performance of an AFD-financed contract;

2.3) Being listed for financial sanctions by the United Nations, the European Union and/or France for the purposes of fight-against-terrorist financing or threat to international peace and security;

2.4) Having been subject within the past five years to a contract termination fully settled against us for significant or persistent failure to comply with our contractual obligations during contract performance, unless this termination was challenged and dispute resolution is still pending or has not confirmed a full settlement against us;

2.5) Not having fulfilled our fiscal obligations regarding payments of taxes in accordance with the legal provisions of either the country where we are constituted or the Contracting Authority's country;

2.6) Being subject to an exclusion decision of the World Bank and being listed on the website http://www.worldbank.org/debarr  (in the event of such exclusion, you may attach to this Statement of Integrity supporting information showing that this exclusion is not relevant in the context of this Contract);

2.7) Having created false documents or committed misrepresentation in documentation requested by the Contracting Authority as part of the procurement process of this Contract.

- We hereby certify that neither we, nor any of the members of our joint venture or any of our suppliers, contractors, subcontractors, consultants or subconsultants are in any of the following situations of conflict of interest:

3.1) Being an affiliate controlled by the Contracting Authority or a shareholder controlling the Contracting Authority, unless the stemming conflict of interest has been brought to the attention of AFD and resolved to its satisfaction;

3.2) Having a business or family relationship with a Contracting Authority's staff involved in the procurement process or the supervision of the resulting Contract, unless the stemming conflict of interest has been brought to the attention of AFD and resolved to its satisfaction;

3.3) Being controlled by or controlling another bidder or consultant, or being under common control with another bidder or consultant, or receiving from or granting subsidies directly or indirectly to another bidder or consultant, having the same legal representative as another bidder or consultant, maintaining direct or indirect contacts with another bidder or consultant which allows us to have or give access to information contained in the respective applications, bids or proposals, influencing them or influencing decisions of the Contracting Authority;

3.4) Being engaged in a consulting services activity, which, by its nature, may be in conflict with the assignments that we would carry out for the Contracting Authority;

3.5) In the case of procurement of goods, works or plants:

- Having prepared or having been associated with a consultant who prepared specifications, drawings, calculations and other documentation to be used in the procurement process of this Contract;

- Having been recruited (or being proposed to be recruited) ourselves or any of our affiliates, to carry out works supervision or inspection for this Contract;

- If we are a state-owned entity, and to compete in a procurement process, we certify that we have legal and financial autonomy and that we operate under commercial laws and regulations.

- We undertake to bring to the attention of the Contracting Authority, which will inform AFD, any change in situation with regard to points 2 to 4 here above.

- In the context of the procurement process and performance of the corresponding contract:

6.1) We have not and we will not engage in any dishonest conduct (act or omission) deliberately indented to deceive others, to intentionally conceal items, to violate or vitiate someone's consent, to make them circumvent legal or regulatory requirements and/or to violate their internal rules in order to obtain illegitimate profit;

6.2) We have not and we will not engage in any dishonest conduct (act or omission) contrary to our legal or regulatory obligations or our internal rules in order to obtain illegitimate profit;

6.3) We have not promised, offered or given and we will not promise, offer or give, directly or indirectly to (i) any Person who holds a legislative, executive, administrative or judicial mandate within the State of the Contracting Authority regardless of whether that Person was nominated or elected, regardless of the permanent or temporary, paid or unpaid nature of the position and regardless of the hierarchical level the Person occupies, (ii) any other Person who performs a public function, including for a State institution or a State-owned company, or who provides a public service, or (iii) any other person defined as a Public Officer by the national laws of the Contracting Authority’s country, an undue advantage of any kind, for himself or for another Person or entity, for such Public Officer to act or refrain from acting in his official capacity;

6.4) We have not promised, offered or given and we will not promise, offer or give, directly or indirectly to any Person who occupies an executive position in a private sector entity or works for such an entity, regardless of the nature of his/her capacity, any undue advantage of any kind, for himself or another Person or entity for such Person to perform or refrain from performing any act in breach of its legal, contractual or professional obligations;

6.5) We have not and we will not engage in any practice likely to influence the contract award process to the detriment of the Contracting Authority and, in particular, in any anti-competitive practice having for object or for effect to prevent, restrict or distort competition, namely by limiting access to the market or the free exercise of competition by other undertakings;

6.6) Neither we nor any of the members of our joint venture or any of our suppliers, contractors, subcontractors, consultants or subconsultants shall acquire or supply any equipment nor operate in any sectors under an embargo of the United Nations, the European Union or France;

6.7) We commit ourselves to comply with and ensure that all of our suppliers, contractors, subcontractors, consultants or subconsultants comply with international environmental and labour standards, consistent with laws and regulations applicable in the country of implementation of the Contract, including the fundamental conventions of the International Labour Organisation (ILO) and international environmental treaties. Moreover, we shall implement environmental and social risks mitigation measures when specified in the environmental and social commitment plan (ESCP) provided by the Contracting Authority.

- We, as well as members of our joint venture and our suppliers, contractors, subcontractors, consultants or subconsultants authorise AFD to inspect accounts, records and other documents relating to the procurement process and performance of the contract and to have them audited by auditors appointed by AFD.

Name: 		In the capacity of:

Duly empowered to sign in the name and on behalf of:

Signature:				Dated:

Schedules of Rates and Prices

(All schedules of rates and prices shall clearly specify the applicable taxes)

Schedule No. 1.  Plant and Mandatory Spare Parts Supplied from Abroad

| Item | Description | Code1 | Qty. | Unit Price2 |  | Total Price2 |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | CIP |  |
|  |  |  | (1) | (2) | (3) | (1) x (3) |
| TOTAL (to Schedule No. 5. Grand Summary) |  |  |  |  |  |  |
|  |  |  | Name of Bidder |  |  |  |
|  |  |  | Signature of Bidder |  |  |  |
| 1 Bidders shall enter a code representing the country of origin of all imported plant and equipment. 2 Specify currency. Create and use as many columns for Unit Price and Total Price as there are currencies. |  |  |  |  |  |  |

Country of Origin Declaration Form

| Item | Description | Code | Country |
| --- | --- | --- | --- |

(All schedules of rates and prices shall clearly specify the applicable taxes)

Schedule No. 2.  Plant and Mandatory Spare Parts Supplied from Within the Employer’s Country

| Item | Description |  |  | Qty. |  | EXW Unit Price1 |  | EXW Total Price1 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | (1) |  | (2) |  | (1) x (2) |  |
| TOTAL (to Schedule No. 5. Grand Summary) |  |  |  |  |  |  |  |  |  |
|  |  |  | Name of Bidder |  |  |  |  |  |  |
|  |  |  | Signature of Bidder |  |  |  |  |  |  |
| 1 Specify currency in accordance with specifications in Bid Data Sheet under ITB 18.1 in Single Stage Bid, or ITB 30.1 in Two Stage Bid. |  |  |  |  |  |  |  |  |  |

(All schedules of rates and prices shall clearly specify the applicable taxes)

Schedule No. 3.  Design Services

| Item | Description |  | Qty. | Unit Price1 |  |  |  | Total Price1 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Local Currency Portion |  | Foreign Currency Portion |  |  |
|  |  |  | (1) | (2) |  | (optional) |  | (1) x (2) |
| TOTAL (to Schedule No. 5. Grand Summary) |  |  |  |  |  |  |  |  |
|  |  |  |  | Name of Bidder |  |  |  |  |
|  |  |  |  | Signature of Bidder |  |  |  |  |
| 1 Specify currency in accordance with specifications in Bid Data Sheet under ITB 18.1 in Single Stage Bid, or ITB 30.1 in Two Stage Bid. |  |  |  |  |  |  |  |  |

(All schedules of rates and prices shall clearly specify the applicable taxes)

Schedule No. 4.  Installation and Other Services

| Item | Description | Qty. | Unit Price1 |  |  |  | Total Price1 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Foreign Currency Portion |  | Local Currency Portion |  | Foreign |  | Local |
|  |  | (1) | (2) |  | (3) |  | (1) x (2) |  | (1) x (3) |
| TOTAL (to Schedule No. 5. Grand Summary) |  |  |  |  |  |  |  |  |  |
|  |  |  | Name of Bidder |  |  |  |  |  |  |
|  |  |  | Signature of Bidder |  |  |  |  |  |  |
| 1 Specify currency in accordance with specifications in Bid Data Sheet under ITB 18.1 in Single Stage Bid, or ITB 30.1 in Two Stage Bid. |  |  |  |  |  |  |  |  |  |

(All schedules of rates and prices shall clearly specify the applicable taxes)

Schedule No. 5.  Grand Summary

| Item | Description |  |  |  | Total Price1 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Foreign |  | Local |  |
|  | Total Schedule No. 1. Plant, and Mandatory Spare Parts Supplied from Abroad |  |  |  |  |  |  |  |
|  | Total Schedule No. 2. Plant, and Mandatory Spare Parts Supplied from Within the Employer’s Country |  |  |  |  |  |  |  |
|  | Total Schedule No. 3. Design Services |  |  |  |  |  |  |  |
|  | Total Schedule No. 4. Installation and Other Services |  |  |  |  |  |  |  |
| TOTAL (to Bid Form) |  |  |  |  |  |  |  |  |
|  |  |  | Name of Bidder |  |  |  |  |  |
|  |  |  | Signature of Bidder |  |  |  |  |  |
| 1 Specify currency in accordance with specifications in Bid Data Sheet under ITB 18.1 in Single Stage Bid, or ITB 30.1 in Two Stage Bid. Create and use as many columns for Foreign Currency requirement as there are foreign currencies |  |  |  |  |  |  |  |  |

(All schedules of rates and prices shall clearly specify the applicable taxes)

Schedule No. 6.  Recommended Spare Parts

| Item | Description |  | Qty. | Unit Price |  |  | Total Price |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | CIF or CIP (foreign parts) |  | EXW (local parts) |  |  |
|  |  |  | (1) | (2) |  | (3) | (1) x (2) or(3) |  |
|  |  |  | Name of Bidder |  |  |  |  |  |
|  |  |  | Signature of Bidder |  |  |  |  |  |

Price Adjustment

Where the Contract Period (excluding the Defects Liability Period) exceeds eighteen (18) months, it is normal procedure that prices payable to the Contractor shall be subject to adjustment during the performance of the Contract to reflect changes occurring in the cost of labor and material components. In such cases the bidding documents shall include in this form a formula of the following general type, pursuant to PC Sub-Clause 11.2. Where Contracts are of a shorter duration than eighteen (18) months or in cases where there is to be no Price Adjustment, the following provision shall not be included. Instead, it shall be indicated under this form that the prices are to remain firm and fixed for the duration of the Contract.

Sample Price Adjustment Formula

Prices payable to the Contractor, in accordance with the Contract, shall be subject to adjustment during performance of the Contract to reflect changes in the cost of labor and material components, in accordance with the following formula:

in which:

P1	=	adjustment amount payable to the Contractor

P0	=	Contract price (base price)

a	=	percentage of fixed element in Contract price (a =   %)

b	=	percentage of labor component in Contract price (b =  %)

c	=	percentage of material and equipment component in Contract price (c =  %)

L0, L1	=	labor indices applicable to the appropriate industry in the country of origin on the base date and the date for adjustment, respectively

M0, M1=	material and equipment indices in the country of origin on the base date and the date for adjustment, respectively

N.B.  a+b+c= 100%.

Conditions Applicable To Price Adjustment

The Bidder shall indicate the source of labor and materials indices and the base date indices in its bid.

Item	Source of Indices Used	Base Date Indices

The base date shall be the date thirty (30) days prior to the Bid closing date.

The date of adjustment shall be the mid-point of the period of manufacture or installation of component or Plant.

The following conditions shall apply:

(a)	No price increase will be allowed beyond the original delivery date unless covered by an extension of time awarded by the Employer under the terms of the Contract.  No price increase will be allowed for periods of delay for which the Contractor is responsible.  The Employer will, however, be entitled to any price decrease occurring during such periods of delay.

(b)	If the currency in which the Contract price, P0, is expressed is different from the currency of the country of origin of the labor and/or materials indices, a correction factor will be applied to avoid incorrect adjustments of the Contract price.  The correction factor shall correspond to the ratio of exchange rates between the two currencies on the base date and the date for adjustment as defined above.

(c)	No price adjustment shall be payable on the portion of the Contract price paid to the Contractor as an advance payment.

Technical Proposal

- Site Organization

- Method Statement

- Mobilization Schedule

- Construction Schedule

- Plant

- Contractor’s Equipment

- Personnel

- Proposed Subcontractors for Major Items of Plant and Installation Services

- Others

Site Organization

[insert any details required for Site Organization]

Method Statement

Each Bidder shall set out details of the Method Statement for the Works to demonstrate how it will meet the Employer’s objective and requirements.  As a minimum, the Method Statement shall address the following:

- Details of the arrangements and methods which the Bidder proposes to implement for the construction of the Works, in sufficient detail to demonstrate their adequacy to achieve the requirements of the Contract including completion within the Time for Completion stated in the Particular Conditions of Contract. Shall include at the minimum the following:

  - Engineering – civil and electrical

  - Installation and erection – towers, equipment, and structures

  - Testing and Commissioning

  - Project Management

  - Quality control measures - The Contractor shall give a narration of specific quality control mechanisms measures at design, manufacture, construction, erection, installation, testing and commissioning in accordance with the Employer’s Requirement. The presentation shall also include method of recruitment/selection of the sub-contractors’ /sub suppliers and how they will be supervised.

  - Environmental and Social aspects –The Contractor shall give a narration of expected risks, taking into account local conditions. The Contractor shall demonstrate that he is able to take all necessary measures to protect the environment both on and off site and to prevent personal injuries or damage to public property or other resulting from pollution, noise or other nuisances from methods used for the works in accordance with the ESMP matrix in the Employer’s Requirement.

- Outline of the arrangements of the Bidder to manage coordination of Site access.

- Comments on the geotechnical and subsurface aspects of the Works including materials, material sources and any constraints.

- [Comments on any offshore or waterfront aspects of the Works.]

- Comments on logistics and traffic management [as may be appropriate].

- Outline of the arrangements and organisation of the Bidder to ensure compliance with the Works Requirements.

- Outline of the arrangements of the Bidder to carry out testing upon completion as specified in the Works Requirements.

(h) [Insert other information, as may be appropriate.]

Mobilization Schedule

[insert any details required]

Construction Schedule

Each Bidder shall set out a detailed Program and Schedule for mobilisation and construction of the Works to be performed, including estimated starting and finishing dates for individual components and identification of major milestones and critical path. The proposed Program and Schedule shall be developed according to Works Requirements and shall address the following:

- Details of the proposed schedule for obtaining permits that may be necessary in order to commence the Works, including the preparation of required studies, supporting information, and applications.

- Details of the proposed timeline for carrying out the Works within the Time for Completion, in the form of a bar chart showing notably the critical path.

- Details of the proposed timeline for the testing, commissioning and handing over of the completed Works.

- A comprehensive outage plan in accordance with the Employer’s Requirements for the shut down time required for implementation of the activities for OHL and OPGW connections. The bidders must demonstrate they are technically able to implement the project with minimal outage and in the most efficient way. A method statement along with schematic drawing, brief activity list, work sequence, time and resource schedule shall also be provided with the bid.

- [Other proposed measures as may be appropriate].

Plant

[insert any details required]

Form FUNC

The Bidder shall copy in the left column of the table below, the identification of each functional guarantee required in the Specification and stated by the Employer in para. 1.2 (c) (or 1.1 (c) for the second stage of a two-stage bidding) of Section III. Evaluation and Qualification Criteria, and in the right column, provide the corresponding value for each functional guarantee of the proposed plant and equipment.

| Required Functional Guarantee | Value of Functional Guarantee of the Proposed Plant and Equipment |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |
| … |  |

Contractor’s Equipment

Form EQU

The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key Contractor’s equipment listed in Section III, Evaluation and Qualification Criteria. A separate Form shall be prepared for each item of equipment listed, or for alternative equipment proposed by the Bidder.

| Item of equipment |  |  |
| --- | --- | --- |
| Equipment information | Name of manufacturer | Model and power rating |
|  | Capacity | Year of manufacture |
| Current status | Current location |  |
|  | Details of current commitments |  |
| Source | Indicate source of the equipment o Owned o Rented o Leased o Specially manufactured |  |

Omit the following information for equipment owned by the Bidder.

| Owner | Name of owner |  |
| --- | --- | --- |
|  | Address of owner |  |
|  | Telephone | Contact name and title |
|  | Fax | Telex |
| Agreements | Details of rental / lease / manufacture agreements specific to the project |  |

Personnel

Form PER-1

Proposed Personnel

Bidders should provide the names of suitably qualified personnel to meet the specified requirements stated in Section III. The data on their experience should be supplied using the Form below for each candidate.

| 1. | Title of position* |
| --- | --- |
|  | Name |
| 2. | Title of position* |
|  | Name |
| 3. | Title of position* |
|  | Name |
| 4. | Title of position* |
|  | Name |

*As listed in Section III.

Form PER-2

Resume of Proposed Personnel

Name of Bidder

| Position |  |  |
| --- | --- | --- |
| Personnel information | Name | Date of birth |
|  | Professional qualifications |  |
| Present employment | Name of employer |  |
|  | Address of employer |  |
|  | Telephone | Contact (manager / personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present employer |

Summarize professional experience over the last 20 years, in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

| From | To | Company / Project / Position / Relevant technical and management experience |
| --- | --- | --- |

Proposed Subcontractors for Major Items of Plant and Installation Services

A list of major items of Plant and Installation Services is provided below.

The following Subcontractors and/or manufacturers are proposed for carrying out the item of the facilities indicated.  Bidders are free to propose more than one for each item

| Major Items of Plant and Installation Services | Proposed Subcontractors/Manufacturers | Nationality |
| --- | --- | --- |

Bidders Qualification following Prequalification

The Bidder shall update the information provided during the corresponding prequalification exercise to demonstrate that he continues to meet the criteria used at the time of prequalification by using the relevant Forms included in this Section. If needed, the Bidder may use any of the Prequalification Forms to notify a change which occurred following the Prequalification.

Form FIN–3.3
Financial Resources

Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject contract or contracts as specified in Section III (Evaluation and Qualification Criteria)

| Financial Resources |  |  |
| --- | --- | --- |
| No. | Source of financing | Amount (US$ equivalent) |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |

Form FIN–3.4
Current Contract Commitments / Works in Progress

Bidders and each member to a JV should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

##### Current Contract Commitments

| ### No. | ### Name of Contract | ### Employer’s Contact Address, Tel, Fax | Value of Outstanding Work [Current US$ Equivalent] | Estimated Completion Date | Average Monthly Invoicing Over Last Six Months [US$/month)] |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |

Bidders Qualification without prequalification (Not Applicable)

To establish its qualifications to perform the contract in accordance with Section III (Evaluation and Qualification Criteria) the Bidder shall provide the information requested in the corresponding Information Sheets included hereunder.

Form ELI-1.1
Bidder Information Form

Date: _________________
ICB No. and title: _________________
Page __________of _______________pages

Bidder's name

In case of Joint Venture (JV), name of each member:

Bidder's actual or intended country of registration: [indicate country of Constitution]

Bidder's actual or intended year of incorporation:

Bidder's legal address [in country of registration]:

Bidder's authorized representative information Name: _____________________________________ Address: ___________________________________ Telephone/Fax numbers: _______________________ E-mail address: ______________________________

1. Attached are copies of original documents of  Articles of Incorporation (or equivalent documents of constitution or association), and/or documents of registration of the legal entity named above.  In case of JV, letter of intent to form JV or JV agreement, in accordance with ITB 4.1.  In case of Government-owned enterprise or institution, in accordance with ITB 4.3 documents establishing: - Legal and financial autonomy - Operation under commercial law - Establishing that the Bidder is not dependent agency of the Employer 2. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

Form ELI-1.2
Bidder's JV Information Form

(to be completed for each member of Bidder’s JV and any Specialized subcontractor if applicable)

Date: _______________
ICB No. and title: __________________
Page _______________ of ____________ pages

Bidder’s JV name:

JV member’s name:

JV member’s country of registration:

JV member’s year of constitution:

JV member’s legal address in country of constitution:

JV member’s authorized representative information Name: ____________________________________ Address: __________________________________ Telephone/Fax numbers: _____________________ E-mail address: _____________________________

1. Attached are copies of original documents of  Articles of Incorporation (or equivalent documents of constitution or association), and/or registration documents of the legal entity named above.  In case of a Government-owned enterprise or institution, documents establishing legal and financial autonomy, operation in accordance with commercial law, and absence of dependent status, in accordance with ITB 4.3. 2. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

Form CON–2
Historical Contract Non-Performance, Pending Litigation and Litigation History

(to be completed by the Bidder and by each member of the Bidder’s JV)

Bidder’s Name: ________________
Date: ______________________
JV Member’s Name_________________________
ICB No. and title: ___________________________
Page _______________of ______________pages

| Non-Performed Contracts in accordance with Section III, Evaluation and Qualification Criteria |  |  |  |
| --- | --- | --- | --- |
|  Contract non-performance did not occur since 1st January [insert current year number less 5] specified in Section III, Evaluation and Qualification Criteria, Sub-Factor 2.1.  Contract(s) not performed since 1st January [insert current year number less 5] specified in Section III, Evaluation and Qualification Criteria, requirement 2.1 |  |  |  |
| Year | Non- performed portion of contract | Contract Identification | Total Contract Amount (current value, currency, exchange rate and US$ equivalent) |
| [insert year] | [insert amount and percentage] | Contract Identification: [indicate complete contract name/ number, and any other identification] Name of Employer: [insert full name] Address of Employer: [insert street/city/country] Reason(s) for non performance: [indicate main reason(s)] | [insert amount] |
| Pending Litigation, in accordance with Section III, Qualification Criteria and Requirements |  |  |  |
|  No pending litigation in accordance with Section III, Qualification Criteria and Requirements, Sub-Factor 2.3. |  |  |  |
|  Pending litigation in accordance with Section III, Evaluation and Qualification Criteria, Sub-Factor 2.3 as indicated below. |  |  |  |

| Year of dispute | Amount in dispute (currency) | Contract Identification | Total Contract Amount (currency), US$ Equivalent (exchange rate) |
| --- | --- | --- | --- |
|  |  | Contract Identification: _________ Name of Employer: ____________ Address of Employer: __________ Matter in dispute: ______________ Party who initiated the dispute: ____ Status of dispute: ___________ |  |

Form FIN–3.1
Financial Situation and Performance

Bidder’s Name: ________________
Date: ______________________
JV Member’s Name_________________________
ICB No. and title: ___________________________
Page _______________of ______________pages

1. Financial data

| Type of Financial information in (currency) | Historic information for previous _________years, ______________ (amount in currency, currency, exchange rate, US$ equivalent) |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Year 1 | Year 2 | Year 3 | Year4 | Year 5 |
| Statement of Financial Position (Information from Balance Sheet) |  |  |  |  |  |
| Total Assets (TA) |  |  |  |  |  |
| Total Liabilities (TL) |  |  |  |  |  |
| Total Equity/Net Worth (NW) |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |
| Current Liabilities (CL) |  |  |  |  |  |
| Working Capital (WC) |  |  |  |  |  |
| Information from Income Statement |  |  |  |  |  |
| Total Revenue (TR) |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |
| Cash Flow Information |  |  |  |  |  |
| Cash Flow from Operating Activities |  |  |  |  |  |

2. Financial documents

The Bidder and its parties shall provide copies of financial statements for ___________years pursuant Section III, Evaluation and Qualifications Criteria, Sub-factor 3.1. The financial statements shall:

(a) 	reflect the financial situation of the Bidder or in case of JV member , and not an affiliated entity  (such as parent company or group member).

(b)	be independently audited or certified in accordance with local legislation.

(c)	be complete, including all notes to the financial statements.

(d)	correspond to accounting periods already completed and audited.

	Attached are copies of financial statements  for the ____________years required above and complying with the requirements

Form FIN–3.2
Average Annual Construction Turnover

Bidder’s Name: ________________
Date: ______________________
JV Member’s Name_________________________
ICB No. and title: ___________________________
Page _______________of ______________pages

|  |  | Annual turnover data (construction only) |  |  |
| --- | --- | --- | --- | --- |
| Year | Amount Currency |  | Exchange rate | US$ equivalent |
| [indicate year] | [insert amount and indicate currency] |  |  |  |
| Average Annual Construction Turnover * |  |  |  |  |

* 	See Section III, Evaluation and Qualification Criteria, Sub-Factor 3.2.

Form FIN–3.3
Financial Resources

Specify proposed sources of financing, such as liquid assets, unencumbered real assets, lines of credit, and other financial means, net of current commitments, available to meet the total construction cash flow demands of the subject contract or contracts as specified in Section III (Evaluation and Qualification Criteria)

| Financial Resources |  |  |
| --- | --- | --- |
| No. | Source of financing | Amount (US$ equivalent) |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |

Form FIN–3.4
Current Contract Commitments / Works in Progress

Bidders and each member to a JV should provide information on their current commitments on all contracts that have been awarded, or for which a letter of intent or acceptance has been received, or for contracts approaching completion, but for which an unqualified, full completion certificate has yet to be issued.

##### Current Contract Commitments

| ### No. | ### Name of Contract | ### Employer’s Contact Address, Tel, Fax | Value of Outstanding Work [Current US$ Equivalent] | Estimated Completion Date | Average Monthly Invoicing Over Last Six Months [US$/month)] |
| --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |
| 4 |  |  |  |  |  |
| 5 |  |  |  |  |  |

Form EXP-4.1
General Construction Experience

(Each Bidder or member of a JV must fill this form)

Bidder’s Name: ________________
Date: ______________________
JV Member’s Name_________________________
ICB No. and title: ___________________________
Page _______________of ______________pages

| Starting Year* | Ending Year | Contract Identification | Role of Bidder |
| --- | --- | --- | --- |
|  |  | Contract name: ____________________ Brief Description of the Works performed by the Bidder: _____________________________ Amount of contract: ___________________ Name of Employer: ____________________ Address: _____________________________ |  |
|  |  | Contract name: _________________________ Brief Description of the Works performed by the Bidder: _____________________________ Amount of contract: ___________________ Name of Employer: ___________________ Address: _________________________ |  |
|  |  | Contract name: ________________________ Brief Description of the Works performed by the Bidder: __________________________ Amount of contract: ___________________ Name of Employer: ___________________ Address: _________________________ |  |

* See Section III Evaluation and Qualification Criteria – Sub Factor 4.1
Form EXP-4.2(a)
Specific Construction and Contract Management Experience

(each Bidder or member of a JV or subcontractor must fill this form)

Bidder’s Name: ________________
Date: ______________________
JV Member’s Name/Subcontractor name_________________________
ICB No. and title: ___________________________
Page _______________of ______________pages

| Similar Contract No. | Information |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Contract Identification |  |  |  |  |  |
| Award date |  |  |  |  |  |
| Completion date |  |  |  |  |  |
| Role in Contract | Prime Contractor  |  | Member in JV  | Management Contractor  | Sub-contractor  |
| Total Contract Amount |  |  |  | US$ equivalent |  |
| If member in a JV or sub-contractor, specify participation in total Contract amount |  |  |  |  |  |
| Employer's Name: |  |  |  |  |  |
| Address: Telephone/fax number E-mail: |  |  |  |  |  |

Form EXP-4.2(a) (cont.)

Specific Construction and Contract Management Experience (cont.)

| Similar Contract No. | Information |
| --- | --- |
| Description of the similarity in accordance with Sub-Factor 4.2(a) of Section III: |  |
| 1. Amount |  |
| 2. Physical size of required works items |  |
| 3. Complexity |  |
| 4. Methods/Technology |  |
| 5. Construction rate for key activities |  |
| 6. Other Characteristics |  |

Form EXP-4.2(b)
Construction Experience in Key Activities

Bidder's Name: ________________
Date: ___________________
Bidder's JV Member Name: __________________
Sub-contractor's Name : ________________
ICB No. and title: _____________________

Page __________________of ________________pages

1.	Key Activity No One: ________________________

|  | Information |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Contract Identification |  |  |  |  |  |  |  |
| Award date |  |  |  |  |  |  |  |
| Completion date |  |  |  |  |  |  |  |
| Role in Contract | Prime Contractor  |  | Member in JV  |  | Management Contractor  | Sub-contractor  |  |
| Total Contract Amount |  |  |  |  | US$ equivalent |  |  |
| Quantity (Volume, number or rate of production, as applicable) performed under the contract per year or part of the year | Total quantity in the contract (i) |  |  | Percentage participation (ii) |  | Actual Quantity Performed (i) x (ii) |  |
| Year 1 |  |  |  |  |  |  |  |
| Year 2 |  |  |  |  |  |  |  |
| Year 3 |  |  |  |  |  |  |  |
| Year 4 |  |  |  |  |  |  |  |
| Employer’s Name: |  |  |  |  |  |  |  |  |
| Address: Telephone/fax number E-mail: |  |  |  |  |  |  |  |  |
| Description of the key activities in accordance with Sub-Factor 4.2(b) of Section III: |  |  |  |  |  |  |

2. Key Activity No. Two

3. …………………

Form of Bid Security (Bank Guarantee)

__________________________

Beneficiary:  __________________________

Date:  __________________________

BID GUARANTEE No.: __________________________

We have been informed that __________________________ (hereinafter called “the Bidder”) has submitted to you its bid dated ___________ (hereinafter called “the Bid”) for the execution of ________________  under Invitation for Bids No. ___________  (“the IFB”).

Furthermore, we understand that, according to your conditions, bids must be supported by a bid guarantee.

At the request of the Bidder, we ____________________ hereby irrevocably undertake to pay you any sum or sums not exceeding in total an amount of ___________  (____________) upon receipt by us of your first demand in writing accompanied by a written statement stating that the Bidder is in breach of its obligation(s) under the bid conditions, because the Bidder:

(a) 	has withdrawn its Bid during the period of bid validity specified by the Bidder in the Form of Bid or any extension thereto provided by the Applicant; or

(b) 	having been notified of the acceptance of its Bid by the Employer during the period of bid validity, (i) fails or refuses to execute the Contract Form, if required, or (ii) fails or refuses to furnish the performance security, in accordance with the ITB.

This guarantee will expire:  (a) if the Bidder is the successful Bidder, upon our receipt of copies of the contract signed by the Bidder and the performance security issued to you upon the instruction of the Bidder; and (b) if the Bidder is not the successful Bidder, upon the earlier of (i) our receipt of a copy your notification to the Bidder of the name of the successful Bidder; or (ii) twenty-eight days after the expiration of the Bidder’s bid.

Consequently, any demand for payment under this guarantee must be received by us at the office on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees, ICC Publication No. 758.

_____________________________

[signature(s)]

Form of Bid-Securing Declaration

Date: ________________

Bid No.: _______________

Alternative No.: _______________

To: ___________________________________

We, the undersigned, declare that:

We understand that, according to your conditions, bids must be supported by a Bid-Securing Declaration.

We accept that we will automatically be suspended from being eligible for bidding in any contract with the Borrower for the period of time of ________________, starting on ____________, if we are in breach of our obligation(s) under the bid conditions, because we:

(a) 	have withdrawn our Bid during the period of bid validity specified in the Letter of Bid or any extension thereto provided by us; or

(b) 	having been notified of the acceptance of our Bid by the Employer during the period of bid validity, (i) fail or refuse to execute the Contract, if required, or (ii) fail or refuse to furnish the Performance Security, in accordance with the ITB.

We understand this Bid-Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of your notification to us of the name of the successful Bidder; or (ii) twenty-eight days after the expiration of our Bid.

Signed: _________________________________ 
In the capacity of ______________________

Name: ______________________________________________________

Duly authorized to sign the bid for and on behalf of: __________________

Dated on ____________ day of __________________, _______ ________________________

Corporate Seal (where appropriate)

Manufacturer’s Authorization

Date: __________________

ICB No.: _________________

To:  ________________________

WHEREAS

We ___________________, who are official manufacturers of ____________________, having factories at _____________________, do hereby authorize ______________________ to submit a bid the purpose of which is to provide the following goods, manufactured by us _______________________, and to subsequently negotiate and sign the Contract.

We hereby extend our full guarantee and warranty in accordance with Clause 27 of the General Conditions, with respect to the goods offered by the above firm.

Signed: _______________________________________

Name: ______________________________________

Title:______________________________________

Duly authorized to sign this Authorization on behalf of: ______________________________________

Dated on ____________ day of __________________, _______

Section V.  Eligibility criteria and social and environmental responsibility

Eligibility in AFD-Financed Procurement

- Financing allocated by the AFD to a Contracting Authority has been entirely untied since 1st January 2002. To the exception of any equipment or any sector which is subject to an embargo by the United Nations, the European Union or France, all goods, works, plants, consulting services and non-consulting services are eligible for the AFD financing regardless of the country of origin of the supplier, contractor, subcontractor, consultant or subconsultant inputs or resources used in the implementation processes. The Contracting Authority means the Purchaser, the Employer, the Client, as the case may be, for the procurement of goods, works, plants, consulting services or non-consulting services.

- Natural or legal persons (including all members of a joint venture or any of their suppliers, contractors, subcontractors, consultants or subconsultants) shall not be awarded an AFD-financed contract if, on the date of submission of an application, a bid or a proposal, or on the date of award of a contract, they:

2.1) Are bankrupt or being wound up or ceasing their activities, are having their activities administered by the courts, have entered into receivership, or are in any analogous situation arising from a similar procedure;

2.2) Have been:

a.  convicted, within the past five years by a court decision, which has the force of res judicata in the country where the contract is implemented, of fraud, corruption or of any other offense committed during a procurement process or performance of a contract, unless they provide supporting information together with their Statement of Integrity (Form available as Appendix to the Application, Bid or Proposal Submission Form) which shows that this conviction is not relevant in the context of this contract;

b. subject to an administrative sanction within the past five years by the European Union or by the competent authorities of the country where they are constituted, for fraud, corruption or for any other offense committed during a procurement process or performance of a contract, unless they provide supporting information together with their Statement of Integrity (Form available as Appendix to the Application, Bid or Proposal Submission Form) which shows that this sanction is not relevant in the context of this contract;

c. convicted, within the past five years by a court decision, which has the force of res judicata, of fraud, corruption or of any other offense committed during the procurement process or performance of an AFD-financed contract;

2.3) Are listed for financial sanctions by the United Nations, the European Union and/or France for the purposes of fight-against-terrorist financing or threat to international peace and security;

2.4) Have been subject within the past five years to a contract termination fully settled against them for significant or persistent failure to comply with their contractual obligations during contract performance, unless this termination was challenged and dispute resolution is still pending or has not confirmed a full settlement against them;

2.5) Have not fulfilled their fiscal obligations regarding payments of taxes in accordance with the legal provisions of either the country where they are constituted or the Contracting Authority's country;

2.6) Are subject to an exclusion decision of the World Bank and are listed on the website http://www.worldbank.org/debarr, unless they provide supporting information together with their Statement of Integrity (Form available as Appendix to the Application, Bid or Proposal Submission Form) which shows that this exclusion is not relevant in the context of this contract;

2.7) Have created false documents or committed misrepresentation in documentation requested by the Contracting Authority as part of the procurement process of this Contract.

- State-owned entities may compete only if they can establish that they (i) are legally and financially autonomous, and (ii) operate under commercial law. To be eligible, a state-owned entity shall establish to the AFD’s satisfaction, through all relevant documents, including its Charter and other information the AFD may request, that it: (i) is a legal entity separate from their state (ii) does not currently receive substantial subsidies or budget support; (iii) operates like any commercial enterprise, and, inter alia, is not obliged to pass on its surplus to their state, can acquire rights and liabilities, borrow funds and be liable for repayment of its debts, and can be declared bankrupt.

Section VI. Agency Policy - Corrupt and Fraudulent Practices – Social and Environmental Responsibility

- Corrupt and Fraudulent Practices

The Contracting Authority and the suppliers, contractors, subcontractors, consultants or subconsultants must observe the highest standard of ethics during the procurement process and performance of the contract. The Contracting Authority means the Purchaser, the Employer, the Client, as the case may be, for the procurement of goods, works, plants, consulting services or non-consulting services.

By signing the Statement of Integrity the suppliers, contractors, subcontractors, consultants or subconsultants declare that (i) “it did not engage in any practice likely to influence the contract award process to the Contracting Authority’s detriment, and that it did not and will not get involved in any anti-competitive practice”, and that (ii) “the procurement process and the performance of the contract did not and shall not give rise to any act of corruption or fraud”.

Moreover, the AFD requires including in the Procurement Documents and AFD-financed contracts a provision requiring that suppliers, contractors, subcontractors, consultants or subconsultants will permit the AFD to inspect their accounts and records relating to the procurement process and performance of the AFD-financed contract, and to have them audited by auditors appointed by the AFD.

The AFD reserves the right to take any action it deems appropriate to check that these ethics rules are observed and reserves, in particular, the rights to:

- Reject a proposal for a contract award if it is established that during the selection process the Bidder or consultant that is recommended for the award has been convicted of corruption, directly or by means of an agent, or has engaged in fraud or anti-competitive practices in view of being awarded the Contract;

- Declare misprocurement when it is established that, at any time, the Contracting Authority, the suppliers, contractors, subcontractors, consultants or subconsultants their representatives have engaged in acts of corruption, fraud or anti-competitive practices during the procurement process or performance of the contract without the Contracting Authority having taken appropriate action in due time satisfactory to the AFD to remedy the situation, including by failing to inform the AFD at the time they knew of such practices.

The AFD defines, for the purposes of this provision, the terms set forth below as follows :

- Corruption of a Public Officer means:

- The act of promising, offering or giving to a Public Officer, directly or indirectly, an undue advantage of any kind for himself or for another person or entity, for such Public Officer to act or refrain from acting in his official capacity; or

- The act by which a Public Officer solicits or accepts, directly or indirectly, an undue advantage of any kind for himself or for another person or entity, for such Public Officer to act or refrain from acting in his official capacity.

- A Public Officer shall be construed as meaning:

- Any person who holds a legislative, executive, administrative or judicial mandate (within the country of the Contracting Authority) regardless of whether that person was nominated or elected, regardless of the permanent or temporary, paid or unpaid nature of the position and regardless of the hierarchical level the person occupies;

- Any other person who performs a public function, including for a State institution or a State-owned company, or who provides a public service;

- Any other person defined as a Public Officer by the national laws of the country of the Contracting Authority.

- Corruption of a private person means:

- The act of promising, offering or giving to any person other than a Public Officer, directly or indirectly, an undue advantage of any kind for himself or for another person or entity, for such person to perform or refrain from performing any act in breach of its legal, contractual or professional obligations; or

- The act by which any person other than a Public Officer solicits or accepts, directly or indirectly, an undue advantage of any kind for himself or for another person or entity, for such person to perform or refrain from performing any act in breach of its legal, contractual or professional obligations;

- Fraud means any dishonest conduct (act or omission), whether or not it constitutes a criminal offence, deliberately intended to deceive others, to intentionally conceal items, to violate or vitiate consent, to circumvent legal or regulatory requirements and/or to violate internal rules in order to obtain illegitimate profit.

- Anti-competitive practices mean:

- Any concerted or implied practices which have as their object or effect the prevention, restriction or distortion of competition within a marketplace, especially where they (i) limit access to the marketplace or free exercise of competition by other undertakings, (ii) prevent free, competition-driven price determination by artificially causing price increases or decreases, (iii) restrict or control production, markets, investments or technical progress; or (iv) divide up market shares or sources of supply;

- Any abuse by one undertaking or a group of undertakings which hold a dominant position on an internal market or on a substantial part of it;

- Any practice whereby prices are quoted or set unreasonably low, the object of which is to eliminate an undertaking or any of its products from a market or to prevent it from entering the market.

- Social and Environmental Responsibility

In order to promote sustainable development, the AFD seeks to ensure that internationally recognized environmental and social standards are complied with. Candidates for AFD-financed contracts shall consequently undertake in the Statement of Integrity to:

- Comply with and ensure that all their subcontractors, or subconsultants comply with international environmental and labour standards, consistent with applicable law and regulations in the country of implementation of the contract, including the fundamental conventions of the International Labour Organisation (ILO) and international environmental treaties;

- Implement environmental and social risks mitigation measures when specified in the environmental and social management plan (ESMP) provided by the Contracting Authority.

In case of joint venture, insert the name of the joint venture. The person who will sign the application, bid or proposal on behalf of the applicant, bidder or consultant shall attach a power of attorney from the applicant bidder or consultant.

If the most recent set of financial statements is for a period earlier than 12 months from the date of bid, the reason for this should be justified.